## Schedule Instructions
TENDER SCHEDULE PREPARATION INSTRUCTIONS (DIT INTERNAL USE ONLY)
In preparing schedules for incorporation within tender documents the following steps are to be undertaken to provide contract specific tender schedules
This set of schedules, 'Major Works' (#12976918) are intended for use where a single project is being tendered. Where a number of projects are being tendered as a single package of work the 'Major Works, Bundled' schedules (#12054856) are to be used
Step No. | Description
1 | Tender Form - Low Complexity
a) Row 6 – Update contract number and name. Note row 39 of this tab and the equivalent entry on other tabs is updated automatically based on this entry
2 | Required Schedules
a) Review schedules required and delete additional ones as necessary
3 | Checklist
a) Review checklist generally, adjustments to be made to account for any deleted or additional tabs
b) Update contract number in footer
4 | S2 Schedule of Quantities and Prices AND S3 Schedule of Quantities and Rates
a) Update specific entries, e.g. Item D Drainage - enter each relevant culvert type and size, reattaining 'Other' item
b) Update contract number in footer
5 | All Other Tabs
a) Insert additional schedules as required e.g. Earthworks Schedule, Materials Schedule, Proposed Subcontractors etc.
b) Update contract number in footer on all tabs
Note that when a Schedule is amended during Tender, the Revision status in the header needs to be amended for that tab only.

## Tender Form - Major Works
TENDER FORM - MAJOR WORKS
TO THE DIRECTOR:
XXCXXX THE DESIGN AND CONSTRUCTION OF XXXXXXX
I/We the undersigned, do hereby tender to perform the above mentioned works in accordance with the Request for Tender Documents.
| Tendered Sum - Defined Works (exclusive of GST) |  |  |  |  | 0
| Provisional Sum - Defined Works (exclusive of GST) |  |  |  |  | 0
| GST amount |  |  |  |  | 0
| Tendered Sum (inclusive of GST) |  |  |  |  | 0
| I/We acknowledge the receipt of amendments numbered: |  |  |  | X
(Tenderer to insert number of amendments received)
| Tenderers Name: |  | X
| ABN: |  | X
| ACN: |  | X
| Address: |  | X
| Telephone Number: |  | X
| Contact E-mail Address: |  | X
I/We declare that this tender is independent and that there has not been any unlawful collusion with any other potential respondent to the procurement process.
| Signature of Tenderer: |  |  | Name: | X
| Position in Company: |  | X
| Signature of Witness: |  |  | Name of Witness: | X
| Dated the: |  | X | day of: | X | 20 | X
FOR OFFICE USE ONLY
Tender opened on ........./........./......
By ............................................................ ...............................................................................
(Signature of Authorised Officer) (Printed Name of Authorised Officer)
And ............................................................ ...............................................................................
(Signature of Authorised Officer) (Printed Name of Authorised Officer)
TENDER FORM (CONTINUED)
DECLARATION IN RELATION TO UNLAWFUL COLLUSION
XXCXXX THE DESIGN AND CONSTRUCTION OF XXXXXXX
| I | X
| of | X
[insert name and address of declarant]
do hereby declare as follows:
1 | I hold the position of: |  | X
| Within: |  | X
(Tenderer) and that I am authorised to provide this declaration on its behalf.
2 | I confirm that the tender submitted by the Tenderer is independent and that there has not been any unlawful collusion with any other tenderer or party in connection with this tender process. This clause does not apply to any formal joint venture contractual arrangement entered into between the Tenderer and any other person(s), the details of which have been provided to the Principal as part of the tender submitted by the Tenderer.
3 | I confirm that the total value of the goods and/or services to be provided by subcontractors, to the extent
| known at the time of making this declaration, is: |  |  | $ X |  | (including GST)
4 | I understand that if any part of this declaration is found to be false the Principal reserves the right (regardless of any subsequent dealings) to:
· terminate negotiations with the Tenderer;
· terminate consideration of the Tenderer’s bid; and
· terminate any contract between the Tenderer and the Principal in relation to the Project without any obligation on the Principal to make any payment to the Tenderer.
5 | Where subcontract work comprises more than 25% of the value of this tender, the Tenderer is required to a complete list of all subcontractors, the value, and the nature of the work to be provided under each sub-contract, to the extent known at the time of making this declaration. The total provided must be equal to that provided for Clause 3 above. Where this value is 25% or less Tenderers are required to enter 'Nil' within the 'Value of Work' column.
| Subcontractor Name |  |  | Description Of Work |  |  | Value Of Work (Including GST)
| X |  |  | X |  |  | $ X
| X |  |  | X |  |  | $ X
| X |  |  | X |  |  | $ X
| X |  |  | X |  |  | $ X
| TOTAL | [5 empty] | $ X
| Signature: |  |  |  | Date: | X
Note: If the tender is submitted jointly with another party or parties, each party must sign this declaration.

## Checklist
SCHEDULE CHECKLIST FOR TENDER SUBMISSION
For each item please tick the box to indicate that the Schedule has been completed in accordance with Conditions of Tendering Annexure A and included with your tender submission.
Tenderers are required to submit each of these schedules in Microsoft Excel format.
| Tender Form - Major Works | □
S2 | Schedule of Quantities & Prices | □
S3 | Schedule of Quantities & Rates | □
S4 | Schedule of Overheads and Profit | □
S5 | Schedule of Rates for Variations | □
S6 | Schedule of Rates for Dayworks | □
S7 | Published List Selling Price for Bituminous Products | □
S8 | Rise & Fall Content Factors | □
S20 | Working Times | □
S23 | Undertaking of Compliance | □
S24 | Risk Schedule | □
S27 | Parent Company Guarantee | □
S28 | Industry Participation Plan | □

## Schedule Rules & WBS
DIT TENDER SCHEDULE RULES & STANDARD WORK BREAKDOWN STRUCTURE
TENDER SCHEDULE RULES
Tenderers are responsible for the completion of all schedules and ensuring the accuracy of any applicable formulas, the following rules are to be adhered to:
Alphabetic characters used at heading levels must be retained (e.g. item P must remain as 'Traffic Signage, Signals and Controls'), where no relevant items form part of the work headings are to be retained and N/A entered
Numbering of individual items must commence using the assigned alphabetic character for that section and be sequential throughout the schedule, e.g. C1, C2, C3
Line items detailed within the example schedule are considered as the minimum level to which quantities and pricing is to be provided, these example items are not to be combined. Additional line items are to be provided where the schedule requests/as appropriate in these AND in other sections generally.
The 'Unit of Measurement' provided in the schedule template must remain where that schedule item is used. For additional line items entries the unit of measurement applied must be appropriate and as is typically adopted by industry. 'Item' is not acceptable where there is another applicable Unit of Measurement.
The total of the priced items has to include everything necessary to provide all works under the contract and ensure that all formulas applied within this document to arrive at their final tendered amount are correct.
DIT WORK BREAKDOWN STRUCTURE
Item No. | Description
A | ENVIRONMENTAL WORKS
Temporary Environmental Works
Temporary environmental works during construction, such as retention, detention and sedimentation ponds, monitoring, screens, filtering, maintenance of same during construction, protection, preservation & monitoring of Aboriginal sites, protection of flora, fire prevention, waste disposal, dieback and dust control
Noise, vibration, water quality monitoring etc
Pre and post construction property inspections
Permanent Environmental Works
Permanent environmental works, such as retention, detention and sedimentation ponds, monitoring , screens, filtering etc. and maintenance of same for the stipulated contract period.
Provision of fauna habitats, underpasses, overpasses, culverts/tunnels, rope crossings, poles and the like
Noise Barriers, temporary and permanent, including specific noise walls, attenuation measures such as mounds, tree planting where noise attenuation is required.
Property adjustment works, e.g. noise attenuation measures (double glazing, additional insulation etc.)
B | TRAFFIC MANAGEMENT
Traffic Management
Temporary traffic management measures including temporary signage (fixed and variable), personnel and barriers for protection of public, traffic and property
C | SERVICES
Temporary or permanent diversion, relocation or protection of public utilities including (but not limited to) power, communications, gas, water and sewer
Relocation of major public utility infrastructure, such as substations, pump stations, and other fixed utility assets to enable the main works to proceed
Provision of new service runs, associated valves, chambers etc
Note: Each service type is to be separately detailed, sized and priced
D | EARTHWORKS AND DEMOLITION
Earthworks includes the formation of the required lines and levels of the new works, such as:
- Establishment & reinstatement of embankment or road material borrow pits
- Site preparation and clearing, top soil removal, demolition or adjustment of structures (above and below ground, acquired properties etc.), decontamination
- Dewatering
- Excavation to sub-grade levels
- Filling, including cut to fill and imported filling to sub-grade levels
- Ground improvement, including stabilisation and pre-loading activities
- Replacement of unsuitable material
- Foundation treatment
- Formation of batters and trimming
- Spoil handling, storage and disposal activities, including appropriate licences if required
- Associated testing, e.g. material, compaction, contamination etc.
E | RETAINING WALLS
Includes all types of retaining walls, such as:
- Demolition and/or adjustment of existing retaining walls
- Reinforced earth and soil nailed walls, including detailed excavation and backfill
- Cantilever walls, including detailed excavation
- Crib or interlocking walls, including detailed excavation and backfill
- Post and panel walls, including all excavation, structural elements and finishing treatments
- Diaphragm walls, including excavation activities and structural elements
- Shotcrete including all preparation, reinforcement, placement etc
Note: Excavation includes the costs of spoil disposal for the respective element
F | DRAINAGE
Includes the following items of work
- Removal or making safe redundant drainage items
- Box and pipe culverts, including excavation, bedding and backfill, compaction testing
- New or existing altered structural elements (pits, junctions, headwalls etc.) and gabion matting/outfall structures, rock protection or equivalent treatments
- Specific filter layers (excluding where part of a pavement design)
- Kerbing (all types), spoon drains, pedestrian ramps, property crossovers
- Gross pollutant traps, treatment facilities, and the like
- CCTV inspection of drainage network
G | BRIDGES
All bridge construction activities, for all methods including, but not limited to:
- Demolition or adjustment of existing bridges
- Temporary Works: Edge protection barriers, scaffolding
- Earthworks: Detailed excavation, backfilling, disposal of excess spoil
- Reinforced Earth Walls: Strip footing, facing units, capping beam, backfill, monitoring instrumentation
- Piling: Piles by type, diameter and length
- Cast In Situ Concrete: For each of the Abutments, Pile Caps, Piers, Deck, Approach Slab, Wing Walls, Headstock and Other items, where applicable specify details of blinding, concrete, reinforcing, formwork, jointing, block outs and the like
- Structural Steel: Girders, throw screens, handrails, barriers, walkways
- Bridge Deck Surfacing: By type and thickness
- Bridge Lighting: Road, pedestrian and feature lighting components
- Other Bridge Items
Note: For projects with more than one bridge pricing of each bridge is to be provided separately
H | TUNNELS
All tunnel construction activities, for all methods including, but not limited to:
- Demolition or adjustment of existing tunnels
- Mobilisation / demobilisation of tunnel equipment and activities
- Excavation and support
- Tunnel linings
- Tunnel drainage
- Finishing works
- Tunnels services
- Ventilation structures and equipment
- Control buildings and systems
Note: For projects with more than one tunnel pricing of each tunnel is to be provided separately
I | PAVEMENTS
Sub-bases and pavement works for the various pavement solutions, including but not limited to:
- Working platform layers
- Unbound sub-base layers
- Unbound base course layers
- Cement stabilisation
- Associated testing, e.g. material, compaction etc.
Note: Pricing for each pavement type is to be provided separately using specific pavement type headings
J | BITUMINOUS SURFACING / ASPHALT
Upgrades to existing pavements, including planing of existing and new wearing surfaces
Bituminous works for the various pavement solutions, including but not limited to:
- Bound sub-base layers
- Bound base layers
- Bound wearing course layers (asphalt, spray seal etc.)
- Associated testing
Note: Pricing for each asphalt type is to be provided separately using specific asphalt type headings
K | SECONDARY PAVEMENTS
Footpaths and cycleways (concrete, asphalt, paved including associated sub-base and base course layers, testing etc.)
Tactiles
Provision of new and/or alteration of existing property accesses/driveways
Median infill (concrete, rubble)
Concrete roundabout annulus (including associated sub-base and base course layers, testing etc.)
Concrete bus bays (including associated sub-base and base course layers, testing etc.)
L | PAVEMENT MARKING
Removal of existing markings and associated devices
Temporary pavement markings, installation and removal
Longitudinal markings: Lane lines, edge lines, barrier lines, clearway lines etc.
Transverse markings: Chevrons, arrows, symbols, messages, rail box hatchings etc.
Coloured bus and cycle lane markings etc.
Kerb painting
Raised pavement markers: Removal of existing, supply and installation of new
Other pavement marking items: Audio-tactile line marking, pavement bars etc.
M | ROAD FURNITURE
Guardrail and associated terminals: w-beam, wire rope etc.
Bus stops/shelters (new, relocation, modification)
Fencing: pedestrian, property
Rest area and/or street furniture and amenities: bins, tables, shelters, toilets etc.
Bike storage areas (unless associated with rail station)
Car park wheel stops
Removal/demolition of the above items
N | LIGHTING
Demolition of existing lighting infrastructure, removal or filling of existing conduits
Temporary lighting (if poles and bases etc apply)
Light pole footings
Single, double and quad outreach poles (including combo poles)
Luminaires
Pedestrian lighting
Feature lighting
Ducting/conduit
Pits
Switchboards
Testing and Commissioning
O | LANDSCAPING AND URBAN DESIGN
Landscaping Soils
Minor earthworks/formation works
Landscaping / revegetation: trees, grasses, shrubs, turf etc.
Watering Systems
Mulching
Erosion control of landscaping works
Landscape drainage, including associated subsurface drainage
Seed collection
Propagation and nursery storage
Public realm furniture
Feature lighting
Public art
Traffic control and service locations where considered likely as a result of landscaping works occurring beyond the extent of the main project
Maintenance of plantings (e.g. weed control, watering etc.) and hard elements (e.g. graffiti removal) for a given period of time after construction, including traffic control, access equipment, safety requirements etc where this occurs after completion of construction works
P | TRAFFIC SIGNAGE, SIGNALS AND CONTROLS
Traffic Signage
Removal of existing signage
Road signage
Wayfinding signage
Guide posts
Bollards
Pedestrian/bike holding rails
Traffic Signals & Controls
Removal of existing signals and ITS infrastructure
Traffic signals, poles and associated infrastructure (Note: combo poles are to be included within 'N - Lighting')
Ducting
Loops
Testing and Commissioning of Traffic Signals & Controls
Intelligent Transport Systems
ITS and signage gantries
Intelligent transport systems
Permanent ITS signage: variable message, speed limit, lane status etc.
Testing and Commissioning of ITS Systems
Q | RAIL
Trackwork
Rail track complete: ballast, sleepers, rail, rail fittings, track laying, tamping, grinding
Acoustic rail track: track slab, acoustic or vibrating track, track laying, grinding
Turnouts, crossovers, actuators, check points etc. associated with rail installation
Buffer stops including sliding friction, hydraulic and fixed stops
Slewing or adjustment of existing rail track
Removal and disposal of existing track
Overhead Wiring and Poles
Overhead traction power wiring including all associated support structures, catenary wiring and power supply
Trackside posts, gantries and fitting associated with the support of over track wiring
Catenary and power wiring and associated tensioning systems within or outside of tunnels
Transformers, switchgear, insulators, earthing, bonding, registration equipment
Undertrack crossings for overhead wiring installation
Removal of existing wiring and poles
Power Supply and Distribution
Incoming raw supply to substations
Substations
High and low voltage power distribution
Transformers for supply to overhead wiring
Trackside installations for power distribution
Removal of existing power supply and distribution items
Signalling
Signal plans, control tables and design directly associated with signalling
Mechanical and civil works where associated with signalling installation, including the services route where solely for signalling
Control systems, automatic trail protection and control
Interlocking
Trackside installations associated with Signalling, including location cases, track circuits, axle counters, signal posts and signals, compressed air systems, ground frames, under track crossings, and other line side items
Signalling power supply from substation or transformer
Signal boxes and buildings
Removal of existing signalling items
Rail Communications
Public address systems, CCTV, passenger information systems, precise clocks, train radio, SCADA, trackside installations for rail communications
Removal of existing communications items
Combined Services Route
Excavation, backfilling, conduits, pits and markers to provide a trunk route for rail services
Removal of existing combined services route items
Stations, Interchanges, Buildings, Stabling and Maintenance Facilities
Above ground stations including all associated components (platforms, vertical transport etc)
Below ground stations including all associated components (in particular excavation and support)
Active Pedestrian Crossings
Transport Interchanges, including structures, road pavements, lighting, vertical transport, signage etc
Car parks (at grade and multi level), complete including associated access roads, controls, entry/exit boom gates
Rail administration buildings
Stabling buildings
Maintenance facilities
Cleaning facilities
Driver amenities
Public amenities
Ticketing systems
Bike storage lockers / buildings
Other related buildings
Commissioning and Handover
Testing and commissioning of component and integrated systems
Overall commissioning of integrated systems
Handover of completed facilities
Training of operators and management
Accreditation costs associated with regulatory approval
Rolling Stock
Design, procurement, delivery and commissioning
Other Rail Specific Works
Alternative commuter costs: bus substitutes (where not provided by the Principal), network upgrades to facilitate passenger movements etc.
R | OTHER
Any items unable to be reasonably allocated within the previous categories
S | DESIGN
Design management and approvals
Investigations and approvals (may include, structural, geotech, enviro approval, veg survey, veg offset, contam testing, material disposal, heritage approval, water affecting activities permits, pavement design etc.)
Detailed design and documentation
Proof engineering
Independent design verification and certification
Design management during construction
Construction verification and certification
As-building of the works, including survey and documentation as specified
T | ON SITE OVERHEADS
Non-Recurring On-Site Overheads
Mobilisation of plant. equipment and personnel
Establishment of site facilities and associated temporary services
Provision of insurances, bank guarantee fees and other contract approvals
Information management system (Tenderer to specify)
CITB levy
Industry levies
Council permits and fees
Recurring On-Site Overheads
Project management, contract management, site engineer, safety representative, environmental representative etc. Note: Additional entries to be provided for each relevant role/person, nominated personnel are required to align with the organisation chart
Consultants
Community and stakeholder requirements and management
Site vehicles, plant, equipment, scaffolding and small tools etc.
Site accommodation running, services costs and other expenses
Safety, training, inductions and PPE etc.
Testing requirements
Survey requirements
Demobilisation
Demobilisation of plant. equipment and personnel
Dis-establishment of site facilities complete
Site clean-up
Contract works maintenance
Industry and Workplace Participation and Skills Development
Industry participation planning and reporting as per the contract requirements
Upskilling and training including the planning and reporting as per the contract requirements
U | OFF SITE OVERHEADS
Those costs, which by the normally accepted standards of accounting, are incurred by the Contractor offsite but cannot be directly attributed a specific item of work. This includes, but is not limited to, items such as rent and maintenance of head office accommodation, general head office administration and director’s salaries
V | TENDERERS PROFIT MARGIN
Tenderers Profit Margin
W | RISK
Risk
X | PROVISIONAL SUM
Principal Controlled Allowance

## S2 SOQ&P
SCHEDULE 2 SCHEDULE OF QUANTITIES AND PRICES
XXCXXX THE DESIGN AND CONSTRUCTION OF XXXXXXX
SUMMARY OF SCHEDULE OF PRICES
RATES SHALL BE EXCLUSIVE OF GST
Item No. | Description | Amount ($)
A | ENVIRONMENTAL WORKS | 0
B | TRAFFIC MANAGEMENT | 0
C | SERVICES | 0
D | EARTHWORKS AND DEMOLITION | 0
E | RETAINING WALLS | 0
F | DRAINAGE | 0
G | BRIDGES | 0
H | TUNNELS | 0
I | PAVEMENTS | 0
J | BITUMINOUS SURFACING / ASPHALT | 0
K | SECONDARY PAVEMENTS | 0
L | PAVEMENT MARKING | 0
M | ROAD FURNITURE | 0
N | LIGHTING | 0
O | LANDSCAPING AND URBAN DESIGN | 0
P | TRAFFIC SIGNAGE, SIGNALS AND CONTROLS | 0
Q | RAIL | 0
R | OTHER | 0
S | DESIGN | 0
T | ON SITE OVERHEADS | 0
U | OFF SITE OVERHEADS | 0
V | TENDERERS PROFIT MARGIN | 0
W | RISK | 0
X | PROVISIONAL SUM | 0
| TOTAL | 0
SCHEDULE OF QUANTITIES AND PRICES
RATES SHALL BE EXCLUSIVE OF GST
Item No. | Description | Unit of Measurement | Estimated Quantity | Rate $ | Amount $
A | ENVIRONMENTAL WORKS
Temporary Environmental Works
A1 | Sediment Ponds | number
A2 | Silt Fencing | metre
A3 | Shaker Grids | number
A4 | Noise Controls | metre
A5 | Noise Monitoring | weeks
A6 | Vibration Controls | Item
A7 | Vibration Monitoring | weeks
A8 | Dilapidation Reporting - Pre Construction | Item
A9 | Dilapidation Reporting - Post Construction | Item
A10 | Maintenance of Environmental Control Measures | weeks
A11 | Other Temporary Environmental Works: (Tenderer to specify)
Permanent Environmental Works
A12 | Sediment Ponds | number
A13 | Noise Barriers (Tender to specify by type and size) | m
A14 | Property Adjustment Works (Tenderer to specify) | Item
A15 | Other Permanent Environmental Works: (Tenderer to specify)
|  |  |  | Subtotal, ENVIRONMENTAL WORKS | 0
B | TRAFFIC MANAGEMENT
B1 | Temporary Traffic Signage | Item
B2 | Temporary Variable Message Signs | Item
B3 | Temporary Traffic Signals | Item
B4 | Temporary Lighting | Item
B5 | Temporary Traffic Barriers | Item
B6 | Maintenance of Traffic Control Measures | Item
B7 | Other: (Tenderer to specify)
|  |  |  | Subtotal, TRAFFIC MANAGEMENT AND TEMPORARY WORKS | 0
C | SERVICES
C1 | Identification and Location of Services | Item
C2 | Temporary Service Requirements (Tenderer to specify by type and size) | Item
C3 | Relocation of Services (Tenderer to specify by type and size) | Item
C4 | Protection of Services (Tenderer to specify by type and size) | Item
C5 | Provision of New Services: (Tenderer to specify) | Item
C6 | Other Services Works: (Tenderer to specify)
|  |  |  | Subtotal, SERVICES | 0
D | EARTHWORKS AND DEMOLITION
Preparation Works
D1 | Demolition of Existing Buildings, Structures and the like | Item
D2 | Clearing and Grubbing of Vegetated / Demolished Areas | square metre
D3 | Clearing and Grubbing of Nominated Trees | number
D4 | Clearing and Grubbing of Existing Bituminous Surfacing | square metre
D5 | Stripping and Stockpiling of Topsoil Material | square metre
D6 | Dumping/Disposal Costs (Tender to specify) | tonnes
D7 | Saw Cutting of Existing Pavement Edges | metre
D8 | Other Preparation Works Items: (Tenderer to specify)
Bulk Earthworks
D9 | Cut to Fill | cubic metre
D10 | Cut to Spoil | cubic metre
D11 | Import to Fill | cubic metre
D12 | Compliance Testing | Item
D13 | Dumping/Disposal Costs (Tender to specify) | tonnes
D14 | Other Bulk Earthworks Items: (Tenderer to specify)
Detailed Earthworks
D15 | Cut to Fill | cubic metre
D16 | Cut to Spoil | cubic metre
D17 | Import to Fill | cubic metre
D18 | Compliance Testing | Item
D19 | Dumping/Disposal Costs (Tender to specify) | tonnes
D20 | Subgrade Preparation all Areas | square metre
D21 | Formation of Batters and Trimming | square metre
D22 | Other Detailed Earthworks Items: (Tenderer to specify)
Surface Treatments
D23 | Respreading of Topsoil from Stockpile | square metre
D24 | Other Surface Treatments Items: (Tenderer to specify)
|  |  |  | Subtotal, EARTHWORKS AND DEMOLITION | 0
E | RETAINING WALLS
Retaining Wall Type A
E1 | Tenderer to Detail Wall Type and Height | square metre
E2 | Other Items Specific to this Retaining Wall Type: (Tenderer to specify)
Retaining Wall Type B
E3 | Tenderer to Detail Wall Type and Height | square metre
E4 | Other Items Specific to this Retaining Wall Type: (Tenderer to specify)
Other Retaining Wall Items
E5 | Other Retaining Wall Items: (Tenderer to specify)
|  |  | Subtotal, RETAINING WALLS |  | 0
F | DRAINAGE
Drainage Demolition
F1 | Tenderer to List and Detail all Drainage Demolition Items
Drainage Structures
F2 | Tenderer to List and Detail all Drainage Structures | number
Pipes and Box Culverts
F3 | Tenderer to List and Detail all Pipelines | metre
Kerbing
F4 | Tenderer to List and Detail all Kerbing | metre
Other
F5 | Other Drainage Items: (Tenderer to specify)
|  |  | Subtotal, DRAINAGE |  | 0
G | BRIDGES
Temporary Works
G1 | Tenderer to List and Detail all Temporary Works Items
Earthworks
G2 | Tenderer to List and Detail all Earthworks Items
Reinforced Earth Walls
G3 | Tenderer to List and Detail all Reinforced Earth Wall Items
Piling
G4 | Tenderer to List and Detail all Pile Items
Cast In Situ Concrete
G5 | Abutment Items: (Tenderer to Specify)
G6 | Pile Cap Items: (Tenderer to Specify)
G7 | Pier Items: (Tenderer to Specify)
G8 | Deck Items: (Tenderer to Specify)
G9 | Approach Slab Items: (Tenderer to Specify)
G10 | Wing Wall Items: (Tenderer to Specify)
G11 | Headstock Items: (Tenderer to Specify)
G12 | Other Cast In-Situ Concrete Items: (Tenderer to Specify)
Structural Steel
G13 | Tenderer to List and Detail all Structural Steel Items
Bridge Deck Surfacing
G14 | Tenderer to List and Detail all Bridge Deck Surfacing Items
Bridge Lighting
G15 | Tenderer to List and Detail all Bridge Lighting Items
Other Bridge Items
G16 | Tenderer to List and Detail all Other Bridge Items
|  |  | Subtotal, BRIDGES |  | 0
H | TUNNELS
H1 | Mobilisation / Demobilisation of Tunnel Equipment and Activities
H2 | Excavation and Support (Tenderer to specify)
H3 | Tunnel Linings (Tenderer to specify)
H4 | Tunnel Drainage (Tenderer to specify)
H5 | Finishing Works (Tenderer to specify)
H6 | Tunnels Services (Tenderer to specify)
H7 | Ventilation Structures and Equipment (Tenderer to specify)
H8 | Control Buildings and Systems (Tenderer to specify)
H9 | Other Tunnel Items: (Tenderer to specify)
|  |  | Subtotal, TUNNELS |  | 0
I | PAVEMENTS
Pavement Type A
I1 | Working Platform / Sub-Base / Base Course Layers (Tenderer to specify by type and layer) | square metre
Pavement Type B
I2 | Working Platform / Sub-Base / Base Course Layers (Tenderer to specify by type and layer) | square metre
Pavement Type C
I3 | Working Platform / Sub-Base / Base Course Layers (Tenderer to specify by type and layer) | square metre
Other Pavement Items
I4 | Other Pavement Items: (Tenderer to specify)
|  |  | Subtotal, PAVEMENTS |  | 0
J | BITUMINOUS SURFACING / ASPHALT
Pavement Type A
J1 | Prime (Tenderer to specify including application rate) | square metre
J2 | Spray Seal / Asphalt (Tenderer to specify by type and layer) | square metre
J3 | Other Items Specific to this Pavement Type: (Tenderer to specify)
Pavement Type B
J4 | Prime (Tenderer to specify including application rate) | square metre
J5 | Spray Seal / Asphalt (Tenderer to specify by type and layer) | square metre
J6 | Other Items Specific to this Pavement Type: (Tenderer to specify)
Pavement Type C
J7 | Prime (Tenderer to specify including application rate) | square metre
J8 | Spray Seal / Asphalt (Tenderer to specify by type and layer) | square metre
J9 | Other Items Specific to this Pavement Type: (Tenderer to specify)
Other Bituminous Surfacing / Asphalt Items
J10 | Other Bituminous Surfacing / Asphalt Items: (Tenderer to specify)
|  |  |  | Subtotal, BITUMINOUS SURFACING / ASPHALT | 0
K | SECONDARY PAVEMENTS
Footpaths / Cycleway Type A
K1 | Footpath / Cycleway (Tenderer to specify by type and layer) | square metre
K2 | Other Items Specific to this Footpath / Cycleway Type: (Tenderer to specify) | square metre
Footpaths / Cycleway Type B
K3 | Footpath / Cycleway (Tenderer to specify by type and layer) | square metre
K4 | Other Items Specific to this Footpath / Cycleway Type: (Tenderer to specify) | square metre
Median Infill Type A
K5 | Median Infill (Tenderer to specify by type and layer) | square metre
K6 | Other Items Specific to this Median Infill Type: (Tenderer to specify) | square metre
Median Infill Type B
K7 | Median Infill (Tenderer to specify by type and layer) | square metre
K8 | Other Items Specific to this Median Infill Type: (Tenderer to specify) | square metre
Other Secondary Pavement Items
K9 | Other Secondary Pavement Items: (Tenderer to specify)
|  |  |  | Subtotal, SECONDARY PAVEMENTS | 0
L | PAVEMENT MARKING
L1 | Removal of Existing Markings and Associated Devices | metre
L2 | Temporary Pavement Markings | metre
L3 | Longitudinal Markings | metre
L4 | Transverse Markings | square metre
L5 | Coloured Lane Markings | square metre
L6 | Kerb Painting | metre
L7 | Raised Pavement Markers | number
L8 | Other Pavement Marking Items: (Tenderer to specify)
|  |  |  | Subtotal, PAVEMENT MARKING | 0
M | ROAD FURNITURE
Barrier Type 1
M1 | Barrier Type 1 (Tender to specify by type) | metre
M2 | Barrier Type 1 Terminals (Tenderer to specify by type) | number
M3 | Other Barrier Items Specific to this Barrier Type (Tender to specify)
Barrier Type 2
M4 | Barrier Type 2 (Tender to specify by type) | metre
M5 | Barrier Type 2 Terminals (Tenderer to specify by type) | number
M6 | Other Barrier Items Specific to this Barrier Type (Tender to specify)
Other Road Furniture Items
M7 | Other Road Furniture Items: (Tenderer to specify)
|  |  |  | Subtotal, ROAD FURNITURE | 0
N | LIGHTING
N1 | Demolition of Existing | Item
N2 | Temporary Lighting Poles, Footings etc | Item
N3 | Footings (Tenderer to specify by type) | number
N4 | Single Outreach Poles (Tenderer to specify by type) | number
N5 | Double Outreach Poles (Tenderer to specify by type) | number
N6 | Luminaires (Tenderer to specify by type) | number
N7 | Conduit (Tenderer to specify by type and size) | metre
N8 | Pits (Tenderer to specify by type and size) | number
N9 | Switchboards (Tenderer to specify by type and size) | number
N10 | Testing and Commissioning | Item
N11 | Other Lighting Items: (Tenderer to specify)
|  |  |  | Subtotal, LIGHTING | 0
O | LANDSCAPING AND URBAN DESIGN
O1 | Landscaping Soils | cubic metre
O2 | Landscaping / Revegetation | square metre
O3 | Watering Systems | number
O4 | Mulching | square metre
O5 | Maintenance of Landscaping (Tender to specify period) | Item
O6 | Other Landscaping and Urban Design Items: (Tenderer to specify)
|  |  |  | Subtotal, LANDSCAPING AND URBAN DESIGN | 0
P | TRAFFIC SIGNAGE, SIGNALS AND CONTROLS
Traffic Signage
P1 | Removal of Existing Signage | Item
P2 | Road Signage (Tender to specify by type) | number
P3 | Guide Posts | number
P4 | Other Traffic Signage Items: (Tenderer to specify)
Traffic Signals & Controls
P5 | Removal of Existing Signals and ITS Infrastructure | Item
P6 | Traffic Signals, Poles, Pits and Associated Infrastructure (Tender to specify by type) | number
P7 | Ducting (Tender to specify by size type) | metre
P8 | Loops | number
P9 | Testing and Commissioning of Traffic Signals & Controls | Item
P10 | Other Traffic Signals & Controls Items: (Tenderer to specify)
Intelligent Transport Systems
P11 | ITS and Signage Gantries (Tender to specify by type) | number
P12 | Intelligent Transport Systems (Tender to specify) | Item
P13 | Permanent ITS Signage (Tender to specify by size and type) | number
P14 | Testing and Commissioning of ITS Systems | Item
P15 | Other Intelligent Transport System Items: (Tenderer to specify)
|  |  |  | Subtotal, TRAFFIC SIGNAGE, SIGNALS AND CONTROLS | 0
Q | RAIL
Trackwork
Q1 | Removal of Existing Track | metre
Q2 | Rail Track Complete (Tenderer to specify) | metre
Q3 | Tamping | metre
Q4 | Turnouts, Crossovers, Actuators etc (Tenderer to specify) | number
Q5 | Other Trackwork Items: (Tenderer to specify)
Overhead Wiring and Poles
Q6 | Removal of Existing Wiring and Poles (Tenderer to specify) | metre
Q7 | Overhead Traction Power Wiring (Tenderer to specify) | Item
Q8 | Trackside posts, gantries and fitting (Tenderer to specify) | Item
Q9 | Catenary Power Wiring and Tensioning Systems (Tenderer to specify) | Item
Q10 | Transformers, Switchgear, Insulators, Earthing, Bonding, Registration Equipment (Tenderer to specify) | Item
Q11 | Other Overhead Wiring and Poles Items: (Tenderer to specify)
Power Supply and Distribution
Q12 | Removal of Existing Power Supply and Distribution Items | Item
Q13 | Incoming Raw Supply to Substations (Tenderer to specify) | Item
Q14 | Substations (Tenderer to specify) | Item
Q15 | High and Low Voltage Power Distribution (Tenderer to specify) | Item
Q16 | Transformers for Supply to Overhead Wiring | Item
Q17 | Trackside Installations for Power Distribution (Tenderer to specify) | Item
Q18 | Other Power Supply and Distribution Items: (Tenderer to specify)
Signalling
Q19 | Removal of Existing Signalling Items | Item
Q20 | Signal Plans, Control Tables and Signalling Design | Item
Q21 | Mechanical and Civil Works for Signalling Installation (including Services Route if Solely for Signalling) | Item
Q22 | Control Systems, Automatic Trail Protection | Item
Q23 | Interlocking | Item
Q24 | Trackside Installations for Signalling (Tenderer to specify) | Item
Q25 | Signalling Power Supply from Substation or Transformer | Item
Q26 | Signal Boxes and Buildings | Item
Q27 | Other Signalling Items: (Tenderer to specify)
Rail Communications
Q28 | Public Address Systems, CCTV, Passenger Information Systems, Precise Clocks, Train Radio, SCADA, Trackside Installations for Rail Communications (Tenderer to specify) | Item
Q29 | Other Rail Communications Items: (Tenderer to specify)
Combined Services Route
Q30 | Excavation, Backfilling, Conduits, Pits and Markers to Provide a Trunk Route for Rail Services (Tenderer to specify) | Item
Q31 | Other Combined Services Route Items: (Tenderer to specify)
Stations, Interchanges, Buildings, Stabling and Maintenance Facilities
Q32 | Stations (Tenderer to specify) | Item
Q33 | Active Pedestrian Crossings (Tenderer to specify) | Item
Q34 | Interchanges (Tenderer to specify) | metre
Q35 | Car Parks (Tenderer to specify) | Item
Q36 | Rail Administration Buildings (Tenderer to specify) | Item
Q37 | Stabling Buildings (Tenderer to specify) | Item
Q38 | Maintenance Facilities (Tenderer to specify) | Item
Q39 | Cleaning Facilities (Tenderer to specify) | Item
Q40 | Other Stations, Interchanges, Buildings, Stabling and Maintenance Facilities Items: (Tenderer to specify)
Commissioning and Handover
Q41 | Testing and Commissioning of Component and Integrated Systems | Item
Q42 | Overall Commissioning of Integrated Systems | metre
Q43 | Handover of Completed Facilities | Item
Q44 | Training of Operators and Management | Item
Q45 | Accreditation Costs Associated with Regulatory Approval | Item
Q46 | Other Commissioning and Handover Items: (Tenderer to specify)
Rolling Stock
Q47 | Design, Procurement, Delivery and Commissioning (Tenderer to specify) | Item
Q48 | Other Rolling stock Items: (Tenderer to specify)
Other Rail Specific Works
Q49 | Alternative Commuter Costs - Bus Substitutes, Network Upgrades to Facilitate Passenger Movements (Tenderer to specify) | Item
Q50 | Other Rail Specific Works Items: (Tenderer to specify)
|  |  |  | Subtotal, RAIL | 0
R | OTHER
R1 | Other Items: (Tenderer to specify)
|  |  |  | Subtotal, OTHER | 0
S | DESIGN
Preliminary Design Functions
S1 | Investigations | Item
S2 | Approvals | Item
S3 | Other: (Tenderer to specify)
Design Gate 1 (e.g. 30%)
S4 | Design Package 1 | Item
S5 | Independent Design Certification Package 1 | Item
S6 | Other: (Tenderer to specify)
Design Gate 2 (e.g. 70%)
S7 | Design Package 1 | Item
S8 | Independent Design Certification Package 1 | Item
S9 | Other: (Tenderer to specify)
Design Gate 3 (e.g. IFC)
S10 | Design Package 1 | Item
S11 | Independent Design Certification Package 1 | Item
S12 | Other: (Tenderer to specify)
Construction Phase Services
S13 | Construction Phase Design Inspections and Reporting | Item
S14 | Other: (Tenderer to specify)
Independent Design Certification
S15 | Independent Design Certification | Item
S16 | Other Independent Design Certification Items: (Tenderer to specify)
Construction Verification
S17 | Construction Verification | Item
S18 | Other Construction Verification Items: (Tenderer to specify)
As Builts
S19 | As Building of the Works, Including Survey and Documentation | Item
S20 | Other As Built Items: (Tenderer to specify)
|  |  |  | Subtotal, DESIGN | 0
T | ON SITE OVERHEADS (Site Specific)
Non-Recurring On Site Overheads
T1 | Mobilisation of Locally Based Personnel | number
T2 | Mobilisation of Interstate Based Personnel | number
T3 | Mobilisation of Locally Based Plant and Equipment | number
T4 | Mobilisation of Interstate Based Plant and Equipment | number
T5 | Establishment of Site Facilities | Item
T6 | Establishment of Temporary Services to Site Facilities | Item
T7 | Provision of Insurances, Bank Guarantee Fees and Other Contract Approvals | Item
T8 | Information Management System (Tenderer to specify) | Item
T9 | CITB Levy | Item
T10 | Other Non-Recurring On-Site Overhead Items: (Tenderer to specify)
Recurring On Site Overheads
T11 | Project Manager | weeks
T12 | Contract Manager | weeks
T13 | Site Engineer | weeks
T14 | Contractors Design Manager | weeks
T15 | Quality Manager | weeks
T16 | Construction Manager | weeks
T17 | Safety Representative | weeks
T18 | Environmental Representative | weeks
T19 | Consultants | weeks
T20 | Community and Stakeholder Requirements and Management | weeks
T21 | Site Vehicles, Plant, Equipment, Scaffolding and Small tools etc. | weeks
T22 | Site Accommodation Running, Services and Expenses | weeks
T23 | Safety, Training, Inductions and PPE etc. | weeks
T24 | Testing Requirements | weeks
T25 | Survey Requirements | weeks
T26 | Other Recurring On-Site Overheads Items: (Tenderer to specify)
Demobilisation
T27 | Demobilisation of Plant. Equipment and Personnel | Item
T28 | Dis-Establishment of Site Facilities Complete | Item
T29 | Site Clean-Up | Item
T30 | Contract Works Maintenance | Item
T31 | Other Demobilisation Items: (Tenderer to specify)
Industry and Workplace Participation and Skills Development
T32 | Industry Participation Planning and Reporting as Per The Contract Requirements | Item
T33 | Upskilling and Training Including The Planning and Reporting as Per The Contract Requirements | Item
T34 | Other Industry and Workplace Participation and Skills Development Items (Tenderer to Specify)
|  |  |  | Subtotal, ON SITE OVERHEADS | 0
U | OFF SITE OVERHEADS
U1 | Off Site Overheads | %
|  |  |  | Subtotal, OFF SITE OVERHEADS | 0
V | TENDERERS PROFIT MARGIN
V1 | Tenderers Profit Margin | %
|  |  |  | Subtotal, TENDERERS MARGIN | 0
W | RISK
W1 | Risk | Item
|  |  |  | Subtotal, RISK | 0
X | PROVISIONAL SUM
X1 | Principal Controlled Allowance | Provisional
|  |  |  | Subtotal, PROVISIONAL SUM | 0

## S3 SOQ&R
SCHEDULE 3 SCHEDULE OF QUANTITIES AND RATES
XXCXXX THE DESIGN AND CONSTRUCTION OF XXXXXXX
SUMMARY OF SCHEDULE OF QUANTITIES AND RATES TOTALS
RATES SHALL BE EXCLUSIVE OF GST
Item No. | Description | Amount ($)
A | ENVIRONMENTAL WORKS | 0
B | TRAFFIC MANAGEMENT | 0
C | SERVICES | 0
D | EARTHWORKS AND DEMOLITION | 0
E | RETAINING WALLS | 0
F | DRAINAGE | 0
G | BRIDGES | 0
H | TUNNELS | 0
I | PAVEMENTS | 0
J | BITUMINOUS SURFACING / ASPHALT | 0
K | SECONDARY PAVEMENTS | 0
L | PAVEMENT MARKING | 0
M | ROAD FURNITURE | 0
N | LIGHTING | 0
O | LANDSCAPING AND URBAN DESIGN | 0
P | TRAFFIC SIGNAGE, SIGNALS AND CONTROLS | 0
Q | RAIL | 0
R | OTHER | 0
S | DESIGN | 0
T | ON SITE OVERHEADS | 0
U | OFF SITE OVERHEADS | 0
V | TENDERERS PROFIT MARGIN | 0
W | RISK | 0
X | PROVISIONAL SUM | 0
| TOTAL | 0
SCHEDULE OF QUANTITIES AND RATES
RATES SHALL BE EXCLUSIVE OF GST
Item No. | Description | Unit of Measurement | Estimated Quantity | Rate $ | Amount $
A | ENVIRONMENTAL WORKS
Temporary Environmental Works
A1 | Sediment Ponds | number
A2 | Silt Fencing | metre
A3 | Shaker Grids | number
A4 | Noise Controls | metre
A5 | Noise Monitoring | weeks
A7 | Vibration Controls | Item
A8 | Vibration Monitoring | weeks
A9 | Dilapidation Reporting - Pre Construction | Item
A10 | Dilapidation Reporting - Post Construction | Item
A11 | Maintenance of Environmental Control Measures | weeks
A12 | Other Temporary Environmental Works: (Tenderer to specify)
Permanent Environmental Works
A12 | Sediment Ponds | number
A13 | Noise Barriers (Tender to specify by type and size) | m
A14 | Property Adjustment Works (Tenderer to specify) | Item
A15 | Other Permanent Environmental Works: (Tenderer to specify)
|  |  |  | Subtotal, ENVIRONMENTAL WORKS | 0
B | TRAFFIC MANAGEMENT
B1 | Temporary Traffic Signage | Item
B2 | Temporary Variable Message Signs | Item
B3 | Temporary Traffic Signals | Item
B4 | Temporary Lighting | Item
B5 | Temporary Traffic Barriers | Item
B7 | Maintenance of Traffic Control Measures | Item
B8 | Other: (Tenderer to specify)
|  |  |  | Subtotal, TRAFFIC MANAGEMENT AND TEMPORARY WORKS | 0
C | SERVICES
C1 | Identification and Location of Services | Item
C2 | Temporary Service Requirements (Tenderer to specify by type and size) | Item
C3 | Relocation of Services (Tenderer to specify by type and size) | Item
C4 | Protection of Services (Tenderer to specify by type and size) | Item
C5 | Provision of New Services: (Tenderer to specify) | Item
C6 | Other Services Works: (Tenderer to specify)
|  |  |  | Subtotal, SERVICES | 0
D | EARTHWORKS AND DEMOLITION
Preparation Works
D1 | Demolition of Existing Buildings, Structures and the like | Item
D2 | Clearing and Grubbing of Vegetated / Demolished Areas | square metre
D3 | Clearing and Grubbing of Nominated Trees | number
D4 | Clearing and Grubbing of Existing Bituminous Surfacing | square metre
D5 | Stripping and Stockpiling of Topsoil Material | square metre
D6 | Dumping/Disposal Costs (Tender to specify) | tonnes
D7 | Saw Cutting of Existing Pavement Edges | metre
D8 | Other Preparation Works Items: (Tenderer to specify)
Bulk Earthworks
D9 | Cut to Fill | cubic metre
D10 | Cut to Spoil | cubic metre
D11 | Import to Fill | cubic metre
D12 | Conformance Testing | Item
D13 | Dumping/Disposal Costs (Tender to specify) | tonnes
D14 | Other Bulk Earthworks Items: (Tenderer to specify)
Detailed Earthworks
D15 | Cut to Fill | cubic metre
D16 | Cut to Spoil | cubic metre
D17 | Import to Fill | cubic metre
D18 | Conformance Testing | Item
D19 | Dumping/Disposal Costs (Tender to specify) | tonnes
D20 | Subgrade Preparation all Areas | square metre
D21 | Formation of Batters and Trimming | square metre
D22 | Other Detailed Earthworks Items: (Tenderer to specify)
Surface Treatments
D23 | Respreading of Topsoil from Stockpile | square metre
D24 | Other Surface Treatments Items: (Tenderer to specify)
|  |  |  | Subtotal, EARTHWORKS AND DEMOLITION | 0
E | RETAINING WALLS
Retaining Wall Type A
E1 | Tenderer to Detail Wall Type and Height | square metre
E2 | Other Items Specific to this Retaining Wall Type: (Tenderer to specify)
Retaining Wall Type B
E3 | Tenderer to Detail Wall Type and Height | square metre
E4 | Other Items Specific to this Retaining Wall Type: (Tenderer to specify)
Other Retaining Wall Items
E5 | Other Retaining Wall Items: (Tenderer to specify)
|  |  | Subtotal, RETAINING WALLS |  | 0
F | DRAINAGE
Drainage Demolition
F1 | Tenderer to List and Detail all Drainage Demolition Items
Drainage Structures
F2 | Tenderer to List and Detail all Drainage Structures | number
Pipes and Box Culverts
F3 | Tenderer to List and Detail all Pipelines | metre
Kerbing
F4 | Tenderer to List and Detail all Kerbing | metre
Other
F5 | Other Drainage Items: (Tenderer to specify)
|  |  | Subtotal, DRAINAGE |  | 0
G | BRIDGES
Temporary Works
G1 | Tenderer to List and Detail all Temporary Works Items
Earthworks
G2 | Tenderer to List and Detail all Earthworks Items
Reinforced Earth Walls
G3 | Tenderer to List and Detail all Reinforced Earth Wall Items
Piling
G4 | Tenderer to List and Detail all Pile Items
Cast In Situ Concrete
G5 | Abutment Items: (Tenderer to Specify)
G6 | Pile Cap Items: (Tenderer to Specify)
G7 | Pier Items: (Tenderer to Specify)
G8 | Deck Items: (Tenderer to Specify)
G9 | Approach Slab Items: (Tenderer to Specify)
G10 | Wing Wall Items: (Tenderer to Specify)
G11 | Headstock Items: (Tenderer to Specify)
G12 | Other Cast In-Situ Concrete Items: (Tenderer to Specify)
Structural Steel
G13 | Tenderer to List and Detail all Structural Steel Items
Bridge Deck Surfacing
G14 | Tenderer to List and Detail all Bridge Deck Surfacing Items
Bridge Lighting
G15 | Tenderer to List and Detail all Bridge Lighting Items
Other Bridge Items
G16 | Tenderer to List and Detail all Other Bridge Items
|  |  | Subtotal, BRIDGES |  | 0
H | TUNNELS
H1 | Mobilisation / Demobilisation of Tunnel Equipment and Activities
H2 | Excavation and Support (Tenderer to specify)
H3 | Tunnel Linings (Tenderer to specify)
H4 | Tunnel Drainage (Tenderer to specify)
H5 | Finishing Works (Tenderer to specify)
H6 | Tunnels Services (Tenderer to specify)
H7 | Ventilation Structures and Equipment (Tenderer to specify)
H8 | Control Buildings and Systems (Tenderer to specify)
H9 | Other Tunnel Items: (Tenderer to specify)
|  |  | Subtotal, TUNNELS |  | 0
I | PAVEMENTS
Pavement Type A
I1 | Working Platform / Sub-Base / Base Course Layers (Tenderer to specify by type and layer) | square metre
Pavement Type B
I2 | Working Platform / Sub-Base / Base Course Layers (Tenderer to specify by type and layer) | square metre
Pavement Type C
I3 | Working Platform / Sub-Base / Base Course Layers (Tenderer to specify by type and layer) | square metre
Other Pavement Items
I4 | Other Pavement Items: (Tenderer to specify)
|  |  | Subtotal, PAVEMENTS |  | 0
J | BITUMINOUS SURFACING / ASPHALT
Pavement Type A
J1 | Prime (Tenderer to specify including application rate) | square metre
J2 | Spray Seal / Asphalt (Tenderer to specify by type and layer) | square metre
J3 | Other Items Specific to this Pavement Type: (Tenderer to specify)
Pavement Type B
J4 | Prime (Tenderer to specify including application rate) | square metre
J5 | Spray Seal / Asphalt (Tenderer to specify by type and layer) | square metre
J6 | Other Items Specific to this Pavement Type: (Tenderer to specify)
Pavement Type C
J7 | Prime (Tenderer to specify including application rate) | square metre
J8 | Spray Seal / Asphalt (Tenderer to specify by type and layer) | square metre
J9 | Other Items Specific to this Pavement Type: (Tenderer to specify)
Other Bituminous Surfacing / Asphalt Items
J10 | Other Bituminous Surfacing / Asphalt Items: (Tenderer to specify)
|  |  |  | Subtotal, BITUMINOUS SURFACING / ASPHALT | 0
K | SECONDARY PAVEMENTS
Footpaths / Cycleway Type A
K1 | Footpath / Cycleway (Tenderer to specify by type and layer) | square metre
K2 | Other Items Specific to this Footpath / Cycleway Type: (Tenderer to specify) | square metre
Footpaths / Cycleway Type B
K3 | Footpath / Cycleway (Tenderer to specify by type and layer) | square metre
K4 | Other Items Specific to this Footpath / Cycleway Type: (Tenderer to specify) | square metre
Median Infill Type A
K5 | Median Infill (Tenderer to specify by type and layer) | square metre
K6 | Other Items Specific to this Median Infill Type: (Tenderer to specify) | square metre
Median Infill Type B
K7 | Median Infill (Tenderer to specify by type and layer) | square metre
K8 | Other Items Specific to this Median Infill Type: (Tenderer to specify) | square metre
Other Secondary Pavement Items
K9 | Other Secondary Pavement Items: (Tenderer to specify)
|  |  |  | Subtotal, SECONDARY PAVEMENTS | 0
L | PAVEMENT MARKING
L1 | Removal of Existing Markings and Associated Devices | metre
L2 | Temporary Pavement Markings | metre
L3 | Longitudinal Markings | metre
L4 | Transverse Markings | square metre
L5 | Coloured Lane Markings | square metre
L6 | Kerb Painting | metre
L7 | Raised Pavement Markers | number
L8 | Other Pavement Marking Items: (Tenderer to specify)
|  |  |  | Subtotal, PAVEMENT MARKING | 0
M | ROAD FURNITURE
Barrier Type 1
M1 | Barrier Type 1 (Tender to specify by type) | metre
M2 | Barrier Type 1 Terminals (Tenderer to specify by type) | number
M3 | Other Barrier Items Specific to this Barrier Type (Tender to specify)
Barrier Type 2
M4 | Barrier Type 2 (Tender to specify by type) | metre
M5 | Barrier Type 2 Terminals (Tenderer to specify by type) | number
M6 | Other Barrier Items Specific to this Barrier Type (Tender to specify)
Other Road Furniture Items
M7 | Other Road Furniture Items: (Tenderer to specify)
|  |  |  | Subtotal, ROAD FURNITURE | 0
N | LIGHTING
N1 | Demolition of Existing | Item
N2 | Temporary Lighting Poles, Footings etc | Item
N3 | Footings (Tenderer to specify by type) | number
N4 | Single Outreach Poles (Tenderer to specify by type) | number
N5 | Double Outreach Poles (Tenderer to specify by type) | number
N6 | Luminaires (Tenderer to specify by type) | number
N7 | Conduit (Tenderer to specify by type and size) | metre
N8 | Pits (Tenderer to specify by type and size) | number
N9 | Switchboards (Tenderer to specify by type and size) | number
N10 | Testing and Commissioning | Item
N11 | Other Road Furniture Items: (Tenderer to specify)
|  |  |  | Subtotal, LIGHTING | 0
O | LANDSCAPING AND URBAN DESIGN
O1 | Landscaping Soils | cubic metre
O2 | Landscaping / Revegetation | square metre
O3 | Watering Systems | number
O4 | Mulching | square metre
O5 | Maintenance of Landscaping (Tender to specify period) | Item
O6 | Other Landscaping and Urban Design Items: (Tenderer to specify)
|  |  |  | Subtotal, LANDSCAPING AND URBAN DESIGN | 0
P | TRAFFIC SIGNAGE, SIGNALS AND CONTROLS
Traffic Signage
P1 | Removal of Existing Signage | Item
P2 | Road Signage (Tender to specify by type) | number
P3 | Guide Posts | number
P4 | Other Traffic Signage Items: (Tenderer to specify)
Traffic Signals & Controls
P5 | Removal of Existing Signals and ITS Infrastructure | Item
P6 | Traffic Signals, Poles, Pits and Associated Infrastructure (Tender to specify by type) | number
P7 | Ducting (Tender to specify by size type) | metre
P8 | Loops | number
P9 | Testing and Commissioning of Traffic Signals & Controls | Item
P10 | Other Traffic Signals & Controls Items: (Tenderer to specify)
Intelligent Transport Systems
P11 | ITS and Signage Gantries (Tender to specify by type) | number
P12 | Intelligent Transport Systems (Tender to specify) | Item
P13 | Permanent ITS Signage (Tender to specify by size and type) | number
P14 | Testing and Commissioning of ITS Systems | Item
P15 | Other Intelligent Transport System Items: (Tenderer to specify)
|  |  |  | Subtotal, TRAFFIC SIGNAGE, SIGNALS AND CONTROLS | 0
Q | RAIL
Trackwork
Q1 | Removal of Existing Track | metre
Q2 | Rail Track Complete (Tenderer to specify) | metre
Q3 | Tamping | metre
Q4 | Turnouts, Crossovers, Actuators etc (Tenderer to specify) | number
Q5 | Other Trackwork Items: (Tenderer to specify)
Overhead Wiring and Poles
Q6 | Removal of Existing Wiring and Poles (Tenderer to specify) | metre
Q7 | Overhead Traction Power Wiring (Tenderer to specify) | Item
Q8 | Trackside posts, gantries and fitting (Tenderer to specify) | Item
Q9 | Catenary Power Wiring and Tensioning Systems (Tenderer to specify) | Item
Q10 | Transformers, Switchgear, Insulators, Earthing, Bonding, Registration Equipment (Tenderer to specify) | Item
Q11 | Other Overhead Wiring and Poles Items: (Tenderer to specify)
Power Supply and Distribution
Q12 | Removal of Existing Power Supply and Distribution Items | Item
Q13 | Incoming Raw Supply to Substations (Tenderer to specify) | Item
Q14 | Substations (Tenderer to specify) | Item
Q15 | High and Low Voltage Power Distribution (Tenderer to specify) | Item
Q16 | Transformers for Supply to Overhead Wiring | Item
Q17 | Trackside Installations for Power Distribution (Tenderer to specify) | Item
Q18 | Other Power Supply and Distribution Items: (Tenderer to specify)
Signalling
Q19 | Removal of Existing Signalling Items | Item
Q20 | Signal Plans, Control Tables and Signalling Design | Item
Q21 | Mechanical and Civil Works for Signalling Installation (including Services Route if Solely for Signalling) | Item
Q22 | Control Systems, Automatic Trail Protection | Item
Q23 | Interlocking | Item
Q24 | Trackside Installations for Signalling (Tenderer to specify) | Item
Q25 | Signalling Power Supply from Substation or Transformer | Item
Q26 | Signal Boxes and Buildings | Item
Q27 | Other Signalling Items: (Tenderer to specify)
Rail Communications
Q28 | Public Address Systems, CCTV, Passenger Information Systems, Precise Clocks, Train Radio, SCADA, Trackside Installations for Rail Communications (Tenderer to specify) | Item
Q29 | Other Rail Communications Items: (Tenderer to specify)
Combined Services Route
Q30 | Excavation, Backfilling, Conduits, Pits and Markers to Provide a Trunk Route for Rail Services (Tenderer to specify) | Item
Q31 | Other Combined Services Route Items: (Tenderer to specify)
Stations, Interchanges, Buildings, Stabling and Maintenance Facilities
Q32 | Stations (Tenderer to specify) | Item
Q33 | Active Pedestrian Crossings (Tenderer to specify) | Item
Q34 | Interchanges (Tenderer to specify) | metre
Q35 | Car Parks (Tenderer to specify) | Item
Q36 | Rail Administration Buildings (Tenderer to specify) | Item
Q37 | Stabling Buildings (Tenderer to specify) | Item
Q38 | Maintenance Facilities (Tenderer to specify) | Item
Q39 | Cleaning Facilities (Tenderer to specify) | Item
Q40 | Other Stations, Interchanges, Buildings, Stabling and Maintenance Facilities Items: (Tenderer to specify)
Commissioning and Handover
Q41 | Testing and Commissioning of Component and Integrated Systems | Item
Q42 | Overall Commissioning of Integrated Systems | metre
Q43 | Handover of Completed Facilities | Item
Q44 | Training of Operators and Management | Item
Q45 | Accreditation Costs Associated with Regulatory Approval | Item
Q46 | Other Commissioning and Handover Items: (Tenderer to specify)
Rolling Stock
Q47 | Design, Procurement, Delivery and Commissioning (Tenderer to specify) | Item
Q48 | Other Rolling stock Items: (Tenderer to specify)
Other Rail Specific Works
Q49 | Alternative Commuter Costs - Bus Substitutes, Network Upgrades to Facilitate Passenger Movements (Tenderer to specify) | Item
Q50 | Other Rail Specific Works Items: (Tenderer to specify)
|  |  |  | Subtotal, RAIL | 0
R | OTHER
R1 | Other Items: (Tenderer to specify)
|  |  |  | Subtotal, OTHER | 0
S | DESIGN
Preliminary Design Functions
S1 | Investigations | Item
S2 | Approvals | Item
S3 | Other: (Tenderer to specify)
Design Gate 1 (e.g. 30%)
S4 | Design Package 1 | Item
S5 | Independent Design Certification Package 1 | Item
S6 | Other: (Tenderer to specify)
Design Gate 2 (e.g. 70%)
S7 | Design Package 1 | Item
S8 | Independent Design Certification Package 1 | Item
S9 | Other: (Tenderer to specify)
Design Gate 3 (e.g. IFC)
S10 | Design Package 1 | Item
S11 | Independent Design Certification Package 1 | Item
S12 | Other: (Tenderer to specify)
Construction Phase Services
S13 | Construction Phase Design Inspections and Reporting | Item
S14 | Other: (Tenderer to specify)
Independent Design Certification
S15 | Independent Design Certification | Item
S16 | Other Independent Design Certification Items: (Tenderer to specify)
Construction Verification
S17 | Construction Verification | Item
S18 | Other Construction Verification Items: (Tenderer to specify)
As Builts
S19 | As Building of the Works, Including Survey and Documentation | Item
S20 | Other As Built Items: (Tenderer to specify)
|  |  |  | Subtotal, DESIGN | 0
T | ON SITE OVERHEADS (Site Specific)
Non-Recurring On Site Overheads
T1 | Mobilisation of Locally Based Personnel | number
T2 | Mobilisation of Interstate Based Personnel | number
T3 | Mobilisation of Locally Based Plant and Equipment | number
T4 | Mobilisation of Interstate Based Plant and Equipment | number
T5 | Establishment of Site Facilities | Item
T6 | Establishment of Temporary Services to Site Facilities | Item
T7 | Other Non-Recurring On-Site Overhead Items: (Tenderer to specify)
Recurring On Site Overheads
T8 | Project Manager | weeks
T9 | Contract Manager | weeks
T10 | Site Engineer | weeks
T11 | Contractors Design Manager | weeks
T12 | Quality Manager | weeks
T13 | Construction Manager | weeks
T14 | Safety Representative | weeks
T15 | Environmental Representative | weeks
T16 | Consultants | weeks
T17 | Community and Stakeholder Requirements and Management | weeks
T18 | Site Vehicles, Plant, Equipment, Scaffolding and Small tools etc. | weeks
T19 | Site Accommodation Running, Services and Expenses | weeks
T20 | Safety, Training, Inductions and PPE etc. | weeks
T21 | Testing Requirements | weeks
T22 | Survey Requirements | weeks
T23 | Other Recurring On-Site Overheads Items: (Tenderer to specify)
Demobilisation
T24 | Demobilisation of Plant. Equipment and Personnel | Item
T25 | Dis-Establishment of Site Facilities Complete | Item
T26 | Site Clean-Up | Item
T27 | Contract Works Maintenance | Item
T28 | Other Demobilisation Items: (Tenderer to specify)
|  |  |  | Subtotal, ON SITE OVERHEADS | 0
U | OFF SITE OVERHEADS
U1 | Off Site Overheads | %
|  |  |  | Subtotal, OFF SITE OVERHEADS | 0
V | TENDERERS PROFIT MARGIN
V1 | Tenderers Profit Margin | %
|  |  |  | Subtotal, TENDERERS MARGIN | 0
W | RISK
W1 | Risk | Item
|  |  |  | Subtotal, RISK | 0
X | PROVISIONAL SUM
X1 | Principal Controlled Allowance | Provisional
|  |  |  | Subtotal, PROVISIONAL SUM | 0

## S4 Overheads & Profit
SCHEDULE 4 SCHEDULE OF OVERHEADS AND PROFIT
ALL RATES SHALL BE EXCLUSIVE OF GST.
| Percentage (all sites) | Delay costs per business day for whole of Works ($)
Recurring On Site Overheads | X | X
Non-recurring On Site Overheads | X
Off Site Overheads | X | X
Profit | X
Number of Working days on which the tender is based: | X
The percentages for overheads and profit in this Schedule must be no greater than the respective amounts in the Schedule of Rates or Schedule of Prices divided by the total of the Contract Sum less onsite overheads, offsite overheads, profit and any provisional sums and provisional quantities.
The Contractor’s Margin is the sum of the percentages listed in this Schedule for Offsite Overheads and Profit.
DESCRIPTION OF OVERHEADS Insert details of where costs such as supervisors, site engineers, managers, vehicles, travel, site accommodation, security, administration and all other substantial overhead items are allocated.
Offsite Overheads: (those costs, which by the normally accepted standards of accounting, are incurred by the Contractor offsite but cannot be directly attributed a specific item of work. This includes, but is not limited to, items such as rent and maintenance of head office accommodation, general head office administration and director’s salaries) :
Recurring Onsite Overheads: For example staff costs, staff expenses (e.g. engineers and supervisors), vehicles, survey, community/stakeholder relations, plant, equipment and small tools.
Non Recurring Onsite Overheads: for example staff accommodation, bank guarantees, mobilisation, demobilisation, IT, insurances, site facilities, site compounds, site security, training, undertakings
Note on B17: DPTI: This cell only required for GC21 contracts

## S5 SOR Variations
SCHEDULE 5 SCHEDULE OF RATES FOR VARIATIONS
ALL ITEMS SHALL BE LISTED AND SHALL BE EXCLUSIVE OF GST
| Description | Unit of Measurement | Rate $
A | UNBOUND PAVEMENTS
A1 | 150mm PM1/20QG | m2
A2 | 200mm PM1/20QG | m2
A3 | 150mm PM2/20QG | m2
A4 | 200mm PM2/20QG | m2
A5 | 325mm PM2/20QG | m2
A6 | Other - Tenderer to nominate
B | ASPHALT
Supply, place, shape, compact the following asphalt materials:
B1 | AMC0 at 1.0L/m2, including surface preparation | m2
B2 | 70mm AC14HB (C320) | m2
B3 | 70mm AC14M (C320) | m2
B4 | 40mm AC10M (A15E) | m2
B5 | 40mm Cold Planing (& reinstatement) | m2
B6 | Other - Tenderer to nominate
C | SPRAY SEAL
C1 | S20E binder at 1.0 L/m2 | m2
C2 | 14mm screenings @ 100m2/m3 | m2
C3 | S20E binder at 0.6 L/m2 | m2
C4 | Seal C170 | m2
C5 | 7mm screenings @ 170m2/m3 | m2
C6 | Other - Tenderer to nominate
D | Other: (Tenderer to Specify)
D1 | Other - Tenderer to nominate

## S6 SOR Dayworks
SCHEDULE 6 SCHEDULE OF RATES FOR DAYWORKS
ALL RATES ARE EXCLUSIVE OF GST
LABOUR
CLASSIFICATION |  | Rate ($) per hour
Project Manager
Design Manager
Structural / Civil Engineer
Site Engineer
Contract Administrator
Supervisor
Survey Officer
Survey Assistant
Leading Hand
Welder
Concreter
Steel fixer
Labourer
PLANT (Rates for plant are all inclusive, e.g. inclusive of operator, fuel, maintenance etc).
ITEM | DESCRIPTION (Make, Year, Model) | Rate ($) per hour
Excavators
Class 20
Class 25
Class 40
Loaders (rubber tyred)
Tenderer to specify
Graders
Tenderer to specify
Backhoes
Tenderer to specify
Compaction Equipment
Three wheel steel drum
Tandem, smooth drum vibrating roller - Class 5
Tandem, smooth drum vibrating roller - Class10
Tandem, smooth drum vibrating roller - Class 12.5
Vibrating plate (small e.g. paving type)
Vibrating plate (large e.g. BPU3345)
Plate compactor (e.g. "Wacker")
Water Cart
Truck
Tenderer to specify
Crane
Tenderer to specify
Light Vehicle
Tenderer to specify
Miscellaneous
Tenderer to specify

## S7 Bit Selling Price
SCHEDULE 7 PUBLISHED LIST SELLING PRICES FOR BITUMINOUS PRODUCTS
ALL RATES ARE EXCLUSIVE OF GST
|  | SUPPLIER | PRICE
1 | The supplier and published list selling price for C170 bitumen is
2 | The supplier and published list selling price for C320 bitumen is
3 | The supplier and published list selling price for polymer is
4 | The supplier and published list selling price for crumb rubber is
5 | The supplier and published list selling price for cutter is

## S8 R&F Content Factors
SCHEDULE 8 RISE AND FALL CONTENT FACTORS
COMPONENT OF WORKS | CONTENT FACTOR
| CL | CF | CM | CP | CB
For items of work which include bituminous products (i.e. spray seals and asphalt). |  | -
For all other items of work which include bituminous products (i.e. items which do not include bituminous products). |  |  |  |  | -
10% is not subject to Rise and Fall
For the purpose of this clause only, the following items in the Schedule of Prices or Schedule of rates are deemed to include bituminous products.
S/R Items within Item J 'Bituminous Surfacing / Asphalt' and Item K 'Secondary Pavements' where these contain spray seals, asphalt and bituminous products

## S20 Working Times
SCHEDULE 20 WORKING TIMES
I/We propose to observe the following working days and hours, vide Clause "Working Days and Hours of Work"
Working Days and Hours
Number of days to be worked per week
|  | X | Days
Number of hours to be worked per day: |  | Tenderer to nominate within the following table
Calendar Name | Working Times | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
ABC-123 | Number of hours to be worked per day (Hours) | X | X | X | X | X | X | X
| Starting Time (AM) | Y | Y | Y | Y | Y | Y | Y
| Finishing Time (PM) | Z | Z | Z | Z | Z | Z | Z
BCD-234 | Number of hours to be worked per day (Hours) | X | X | X | X | X | X | X
| Starting Time (AM) | Y | Y | Y | Y | Y | Y | Y
| Finishing Time (PM) | Z | Z | Z | Z | Z | Z | Z
CDE-345 | Number of hours to be worked per day (Hours) | X | X | X | X | X | X | X
| Starting Time (AM) | Y | Y | Y | Y | Y | Y | Y
| Finishing Time (PM) | Z | Z | Z | Z | Z | Z | Z
Rostered Days Off
Proponent to nominate
XX/XX/XXXX
XX/XX/XXXX
XX/XX/XXXX
Note: Working hours need to make allowance for breaks

## S21 Cash Flow
SCHEDULE 21 CASH FLOW
ALL VALUES ARE EXCLUSIVE OF GST
MONTH NO. | MONTH NAME | SPEND | CUMULATIVE SPEND
1 |  | 0 | 0
2 |  | 0 | 0
3 |  | 0 | 0
4 |  | 0 | 0
5 |  | 0 | 0
6 |  | 0 | 0
7 |  | 0 | 0
8 |  | 0 | 0
9 |  | 0 | 0
10 |  | 0 | 0
11 |  | 0 | 0
12 |  | 0 | 0
13 |  | 0 | 0
14 |  | 0 | 0
15 |  | 0 | 0
16 |  | 0 | 0
17 |  | 0 | 0
18 |  | 0 | 0
19 |  | 0 | 0
20 |  | 0 | 0
21 |  | 0 | 0
22 |  | 0 | 0
23 |  | 0 | 0
24 |  | 0 | 0
| TOTAL | 0 | 0
| TENDERED TOTAL | 0
| ERROR | 0

## S23 Undertaking of Compliance
SCHEDULE 23 UNDERTAKING OF COMPLIANCE
Declaration of Compliance with the Code for the Tendering and Performance of Building Work 2016.
XXCXXX THE DESIGN AND CONSTRUCTION OF XXXXXXX
Name of Tenderer: | X
ABN: | X
ACN: | X
1. The Tenderer confirms that it has complied with the Code for the Tendering and Performance of Building Work 2016 (Building Code) in preparing this Tender.
2. The Tenderer undertakes that it complies with the Building Code, and has complied with the Building Code from the time of lodgement of this tender, and that it will require compliance by its related entities (see Part 1, section 3(2) of the Building Code).
3. The Tenderer undertakes to ensure compliance from all subcontractors and consultants engaged on this project, should it be the successful Tenderer. All contracts must expressly require compliance with the Building Code.
4. The Tenderer agrees that it and its subcontractors and its related entities will provide the Commonwealth or any person authorised by the Commonwealth, including a person occupying a position in the Australian Building and Construction Commission, with access to:
(a) inspect any work, material, machinery, appliance, article or facility;
(b) inspect and copy any record relevant to the Project and Works the subject of this Contract;
(c) interview any person; and
(d) any document requested under this contract. The document must be provided within the period specified either in person, by fax or by post, as is necessary to demonstrate its compliance with the Building Code.
5. The Tenderer acknowledges that it is aware the Commonwealth or Minister for Employment and Workplace Relations may impose a sanction on a Tenderer or Contractor that does not comply with the Building Code.
The sanction imposed may include but is not limited to:
(a) the reporting of the breach to an appropriate statutory body or law enforcement agency (if there is evidence that the breach may also be a breach of a Commonwealth or State law), or industry association;
(b) issuing of a formal warning that future breaches may lead to more significant sanctions;
(c) preclusion from Tendering for any Commonwealth funded building and construction work for a specified period;
(d) communication of sanction details to all Commonwealth agencies to ensure a ‘whole-of-Government’ approach;
(e) publication of details of the breach and identification of the party committing the breach; and
(f) a reduction in the number of tendering opportunities that are given.
6. The Tenderer is to select which of the following clauses in italics is appropriate and delete the remaining clause:
a) The Tenderer hereby gives its consent, and confirms that its related entities give their consent, to disclosure by the Commonwealth, its agencies and ministers, of information concerning the Tenderer’s and its related entities’ compliance with the Building Code and whether or not a sanction has been imposed on the Tenderer and/or related entity of the Tenderer, for the exercise of their statutory and portfolio responsibilities (the Purposes).
OR
b) The Tenderer has previously given its consent, and confirms that its related entities have previously given their consent, to disclosure by the Commonwealth, its agencies and ministers, of information concerning the Tenderer’s and its related entities’ compliance with the Building Code and whether or not a sanction has been imposed on the Tenderer and/or a related entity of the Tenderer for the exercise of their statutory and portfolio responsibilities (the Purposes), and confirms that the Tenderer and its related entities have not revoked that consent.
7. The Tenderer has obtained or will obtain the consent of each subcontractor and consultant proposed in its Tender to disclosure by the Commonwealth, its agencies and ministers, of information concerning the proposed subcontractors, compliance with the Building Code and whether or not a sanction has been imposed on any proposed subcontractor, for the Purposes.
8. The Tenderer acknowledges that the consents provided in clause 6 are not limited to this Tender process as the Tenderer is expected to comply with the Building Code in future projects.
9. The Tenderer will:
(a) Describe how the Tenderer has complied with the Building Code in the past (if the Tenderer has undertaken Australian Government funded construction work in the past) and how it will comply if successful. For example, the tenderer will:
(i) comply with the Building Code;
(ii) require compliance with the Building Code from all subcontractors before doing business with them;
(iii) apply the Building Code to privately funded projects that commence after they first lodge an expression of interest or tender for an Australian Government project;
(iv) ensure that contractual documents allow for a person occupying a position in Fair Work Building Industry to access sites, documents and personnel to monitor compliance with the Building Code, including privately funded construction sites;
(v) ensure project managers or head contractors establish appropriate processes to ensure freedom of association;
(vi) ensure there is a work health safety and rehabilitation (WHS&R) plan for the Project;
(vii) respond to requests for information concerning Building Code-related matters made on behalf of Code Monitoring Group (CMG);
(viii) where practicable, ensure contractors or subcontractors initiate voluntary remedial action aimed at rectifying non-compliant behaviour when it is drawn to their attention;
(ix) ensure that CMG secretariat is notified of any alleged breaches, voluntary remedial action taken or other Building Code-related matters within 21 days of the party becoming aware of the alleged breach; and
(x) be aware that and ensure that sanctions applied under the Building Code are enforced including the exclusion of identified parties from work opportunities in accordance with decisions advised by CMG.
(b) Where the Tenderer proposes to subcontract an element of the work, the Tenderer is either to:
(i) provide the information detailed at (a) in relation to each subcontractor; or
(ii) detail how the Tenderer intends to ensure compliance with the Building Code by each subcontractor.
(c) Ensure that where threatened or actual industrial action occurs on a project, contractors, subcontractors, consultants or project managers report such action to the Funding Entity.
10. Where the tenderer has a Fair Work Act 2009 enterprise agreement that enterprise agreement includes a genuine dispute resolution procedure that includes the following:
(a) the ability for employees to appoint a representative in relation to the dispute;
(b) in the first instance procedures to resolve the dispute at the workplace level;
(c) if a dispute is not resolved at the workplace level, the capacity for a party to the dispute to refer the matter to an independent third party for mediation or conciliation; and
(d) if the dispute is still not resolved, the capacity for an independent third party to settle the dispute via a decision binding on the parties.
(Insert additional sheets for response as necessary)

## S24 Risk Schedule
SCHEDULE 24 RISK SCHEDULE
RATES SHALL BE EXCLUSIVE OF GST
Risk No. | Description | Party responsible for Risk
R1 | Interpretations and opinions contained within reports of any kind supplied by the Principal.
R2 | The location of Utility Services outside of the Reference Design "footprint" and the requirements of the Service Authorities for protection and/relocation.
R2 | The location of Utility Services within the Reference Design "footprint" and the requirements of the Service Authorities for protection and/relocation. | Contractor
R3 | The risk that the physical conditions and characteristics of material are different than those which could be reasonably anticipated from the data and interpretations provided by the Principal. | Contractor*
R4 | The risk that Unsuitable Material, requiring treatment or replacement, (vide Part 210) is encountered. | Contractor*
R5 | The risk that contaminated material in the tram corridor is encountered | Contractor*
R6 | Any other Latent Condition not included above in this table.
R7 | All risks associated with the development of the design and the execution of the works not included above in this table, other than risks specifically reserved to the Principal or elsewhere in this Contract. | Principal*
* Tenderers may submit bids with alternative risk allocation for these items; to be completed in the final contract document.

## S27 Parent Company Guarantee
SCHEDULE 27 PARENT COMPANY GUARANTEE
Insert a copy of the proposed Corporate Guarantee, which must be substantially in the form of the DIT Example Corporate Guarantee, available from http://www.dit.sa.gov.au/contractor_documents/guidelines_and_miscellaneous, or provide evidence why a Corporate Guarantee is not required.
Note on B5: DPTI: Specifiers to confirm wording is appropriate

## S28 IP Plan
SCHEDULE 28 INDUSTRY PARTICIPATION PLAN
Tenderers must complete an Industry Participation Plan (IPP) online at:
www.saipp.sa.gov.au
Tenderers must submit a copy of the completed IPP with the tender.
Guidelines and templates are also available to assist tenderers to understand the detail and information required to meet Industry Participation Policy requirements.
For further assistance with completing the form, please contact the following:
Phone : (08) 8226 8956
Email : oia@sa.gov.au
Address : Level 13, 99 Gawler Place, Adelaide, South Australia 5000