## Work Summary
#REF!
WORK SUMMARY
DEFINED WORK
SITE DETAILS | [10 empty] | Treatment Type | BINDER DETAILS |  |  |  |  | FABRIC DETAILS |  |  | FABRIC DETAILS |  |  | AGGREGATE | [6 empty] | Pavement Marking Required within (days) | Comments
AE No. / xxx | Road Number | Road Name | Road Section | MMP Start | MMP End | Length (m) | Average Width (m) | Long Run Area (m2) | Short Bar & H/spy (m2) | Total Area (m2) |  | Binder Type | Pts Appr Add | App. Rate (l/m2) | Qty (lts) | Est Cutter (Its) | Fabric Area (m2 PF1) | Tack Appl. (l/m2) | Tack Qty (lts Binder Type) | Fabric Area (m2 PF1) | Tack Appl. (l/m2) | Tack Qty (ltrs C170) | Supplied by DTEI | Stack Site No | Location of Stack Site | Size (mm) | Quantity (m3) | Spread Rate (m2/m3) | Precoat Rate (lts/m3)
Total | [9 empty] | 6828 |  |  |  |  | 12974 | 778 | [12 empty] | 11
212 | 4763 | Noarlunga - Cape Jervis | Delamere - Cape Jervis | 68.716 | 69.69 | 960 | 6.8 | 6528 | 300 | 6828 | 14/7mm CR | C170+18parts CR | 1 | 0.95 | 6487 | 389 | [6 empty] | Yes | ER-067-14 | RN 4763 | 14 | 75 | 100 | 4 | 3 | Handspray at Range Rd Junction
[13 empty] | 1 | 0.95 | 6487 | 389 | [7 empty] | ER-067-15 | MMP 68.85 | 7 | 44 | 170 | 7 |  | 1 No side Road
PROVISIONAL WORK
SITE DETAILS | [10 empty] | Treatment Type | BINDER DETAILS |  |  |  |  | FABRIC DETAILS |  |  | FABRIC DETAILS |  |  | AGGREGATE | [6 empty] | Linemarking Required within (days) | Comments
AE No. / xxx | Road Number | Road Name | Road Section | MMP Start | MMP End | Length (m) | Average Width (m) | Long Run Area (m2) | Short Bar & H/spy (m2) | Total Area (m2) |  | Binder Type | Pts Appr Add | App. Rate (l/m2) | Qty (lts) | Est Cutter (Its) | Fabric Area (m2 PF1) | Tack Appl. (l/m2) | Tack Qty (lts Binder Type) | Fabric Area (m2 PF1) | Tack Appl. (l/m2) | Tack Qty (ltrs C170) | Supplied by DTEI | Stack Site No | Location of Stack Site | Size (mm) | Quantity (m3) | Spread Rate (m2/m3) | Precoat Rate (lts/m3)
Total | [9 empty] | 6828 |  |  |  |  | 12974 | 778 | [12 empty] | 11
212 | 4763 | Noarlunga - Cape Jervis | Delamere - Cape Jervis | 68.716 | 69.69 | 960 | 6.8 | 6528 | 300 | 6828 | 14/7mm CR | C170+18parts CR | 1 | 0.95 | 6487 | 389 | [6 empty] | Yes | ER-067-14 | RN 4763 | 14 | 75 | 100 | 4 | 3 | Handspray at Range Rd Junction
[13 empty] | 1 | 0.95 | 6487 | 389 | [7 empty] | ER-067-15 | MMP 68.85 | 7 | 44 | 170 | 7 |  | 1 No side Road

## Pavement Marking Summary
#REF!
PAVEMENT MARKING SUMMARY
DEFINED WORK
AE/xxx | Separation Line |  |  |  | Barrier Line |  | Edge-line |  |  |  | Continuity | Polydot Discs | RPM's |  |  | Pavement Bars | Handsray | Miscellaneous | Traffic Lane Width | Linemarking Required within | Drawing No.
| 3m x 9m | 6m x 6m | Solid 100mm | Solid 200mm | Single | Double | 23m x 1m x 100mm | Solid 100mm | Solid 150mm | Vibraline | 1m x 3m x 100mm | Centreline | Centreline | Edgelines | No. Req. | No. Req | m2 |  |  | (Days)
Total | 0 |  | 0 | 0 | 0 | 1626 | 3352 | 0 | 0 | 0 | 0 |  | 276 | 0 | 276 | 0 | 0
201 | [5 empty] | 813 | 1676 | [5 empty] | 138 |  | 138 |  |  |  | 3.3 | 3
PROVISIONAL WORK
AE/xxx | Separation Line |  |  |  | Barrier Line |  | Edge-line |  |  |  | Continuity | Polydot Discs | RPM's |  |  | Pavement Bars | Handsray | Miscellaneous | Traffic Lane Width | Linemarking Required within | Drawing No.
| 3m x 9m | 6m x 6m | Solid 100mm | Solid 200mm | Single | Double | 23m x 1m x 100mm | Solid 100mm | Solid 150mm | Vibraline | 1m x 3m x 100mm | Centreline | Centreline | Edgelines | No. Req. | No. Req | m2 |  |  | (Days)
Total | 0 |  | 0 | 0 | 0 | 813 | 1676 | 0 | 0 | 0 | 0 |  | 138 | 0 | 138 | 0 | 0
201 | [5 empty] | 813 | 1676 | [5 empty] | 138 |  | 138 |  |  |  | 3.3 | 3

## Tender Form
TENDER FORM
TO THE GENERAL MANAGER:
THE BITUMINOUS SURFACING AND PAVEMENT MARKING OF VARIOUS ROADS IN EASTERN REGION CONTRACT No. XX (2014/15)
I/We the undersigned, do hereby tender to perform the above mentioned works in accordance with the Request for Tender Documents.
Tendered Sum (exclusive of GST)
GST amount
Tendered Sum (inclusive of GST) | 0
I/We acknowledge the receipt of amendments numbered:........................
(Tenderer to insert number of amendments received)
Tenderer's Name ........................................................................................................................................................... (BLOCK LETTERS)
ACN .............................................................. ABN ..............................................................................................
Address .................................................................................................................................................................
Telephone No. .......................................................................................................................................................
Contact E-mail Address ……………………………………………………………………………………..
I/We declare that this tender is independent and that there has not been any unlawful collusion with any other potential respondent to the procurement process.
Signature of Tenderer .............................................. Name ...................................................................................
Position in Company ..............................................................................................................................................
Signature of Witness ............................................ Name of Witness ......................................................................
Dated the ................................................................. day of .........................................20 ....................................
FOR OFFICE USE ONLY
Tender opened on ............./............/2014
By: .................................................................... ...........................................................
(Signature of Authorised Officer) (Printed Name of Authorised Officer)
And: .................................................................... ...........................................................
(Signature of Authorised Officer) (Printed Name of Authorised Officer)
Re: DPTI XXCxxx
I, ………………………………………….…………….of …………………………………………………………….
[insert name and address of declarant]
do hereby declare as follows:
hold the position of ………………………………………………………………………..within …………………….. ……….………………….. ………………………………………(Tenderer) and that I am authorised to provide this declaration on its behalf.
I confirm that the tender submitted by the Tenderer is independent and that there has not been any unlawful collusion with any other tenderer or party in connection with this tender process. This clause does not apply to any formal joint venture contractual arrangement entered into between the Tenderer and any other person(s), the details of which have been provided to the Principal as part of the tender submitted by the Tenderer.
I confirm that the total value of the goods and/or services to be provided by subcontractors, to the extent known at the time of making this declaration, is $...................
I understand that if any part of this declaration is found to be false the Principal reserves the right (regardless of any subsequent dealings) to:
· terminate negotiations with the Tenderer;
· terminate consideration of the Tenderer’s bid; and
· terminate any contract between the Tenderer and the Principal in relation to the Project without any obligation on the Principal to make any payment to the Tenderer.
Where subcontract work comprises more than 25% of the value of this tender, attached hereto is a complete list of all sub-contractors, the value, and the nature of the work to be provided under each sub-contract, to the extent known at the time of making this declaration.
……………………………………….
Signature | Date
Note: If the tender is submitted jointly with another party or parties, each party must sign this declaration.

## Checklist
SCHEDULE CHECKLIST FOR TENDER SUBMISSION
For each item please tick the box to indicate that the Schedule has been completed in accordance with Conditions of Tendering Annexure A and included with your tender submission.
1 |  | □
2 |  | □
□
□
□
□
□
□
□
□
□
□
□
□
□
□
□
Note on B1: DPTI: This Checklist not to be used if all of the Schedules listed in Conditions of Tendering Annexure A have been constructed and inserted.
Note on A5: DTEI: Specifier to construct in accordance with Conditions of Tendering Annexure A.

## S3 Schedule of Rates
SCHEDULE 3 SCHEDULE OF RATES
RATES SHALL BE EXCLUSIVE OF GST
Item No. | Description | Unit of Measurement | Quantity | Rate $ | Amount $
DEFINED WORK
1 | AExxx | square metre |  |  | 0
2 |  |  |  |  | 0
3 |  |  |  |  | 0
TOTAL
MISCELLANEOUS ITEMS
1 | Time Related Costs | hour | 20 (+/- 100%)
2 | Re-establishment | hour | 20 (+/- 100%)
3 | Standby | hour | 20 (+/- 100%)
PROVISIONAL WORK
1 | AExxx | square metre |  |  | 0
2 |  |  |  |  | 0
3 |  |  |  |  | 0
MISCELLANEOUS ITEMS
1 | Time Related Costs | hour | 20 (+/- 100%)
2 | Re-establishment | hour | 20 (+/- 100%)
3 | Standby | hour | 20 (+/- 100%)
PAVEMENT MARKING
1 | Separation Line: 3m x 9m | metre | 0 |  | 0
2 | Separation Line: 6m x 6m | metre | 0 |  | 0
3 | Separation Line: Solid 100mm | metre | 0 |  | 0
4 | Separation Line: Solid 200mm | metre | 0 |  | 0
5 | Barrier Line: Single | metre | 0 |  | 0
6 | Barrier Line: Double | metre | 0 |  | 0
7 | Edge Line: 23m x1m x 100mm | metre | 0 |  | 0
8 | Edge Line: Solid x 100mm | metre | 0 |  | 0
9 | Edge Line: Solid x 150mm | metre | 0 |  | 0
10 | Edge Line: Vibraline | metre | 0 |  | 0
11 | Continuity Line: 1m x 3m x 100mm | metre | 0 |  | 0
12 | Polydots Discs | number | 0 |  | 0
13 | Paised Pavement Markers | number | 0 |  | 0
14 | Pavement Bars | number | 0 |  | 0
15 | Handspray | square metre | 0 |  | 0
TOTAL
MISCELLANEOUS ITEMS
1 | Time Related Costs | hour | 20 (+/- 100%)
2 | Re-establishment | hour | 20 (+/- 100%)
3 | Standby | hour | 20 (+/- 100%)
TOTAL
Note on E15: DPTI: Specifier to nominate hours
Note on E16: DPTI: Specifier to nominate hours
Note on E17: DPTI: Specifier to nominate hours

## S5 SOR Variations
SCHEDULE 5 SCHEDULE OF RATES FOR VARIATIONS
RATES SHALL BE EXCLUSIVE OF GST
Item No. | Description | Unit of Measurement | Rate $
1 | Sweeping | square metre
2 | Binder: Supply, prepare and spray C170 | litre
3 | Binder: Supply, prepare and spray C320 | litre
4 | Binder: Supply, prepare and spray S15E | litre
5 | Binder: Supply, prepare and spray S20E | litre
6 | Binder: Supply, prepare and spray S35E | litre
7 | Binder: Supply, prepare and spray C170 plus 18 parts Crumb Rubber | litre
8 | Additive: Supply and mix in binder | litre
9 | Cutter: Supply and mix in binder | litre
10 | Precoating: Supply and apply to aggregate | litre
11 | Additional rolling T0.5 [T1 (in m2 rate) + 0.5 = T1.5] | square metre
12 | Additional rolling T1.0 [T1 (in m2 rate) + T1 = T2] | square metre

## S7 Selling Price
SCHEDULE 17 PUBLISHED LIST SELLING PRICES FOR BITUMINOUS PRODUCTS
|  | SUPPLIER | PRICE
1 | The supplier and published list selling price for C170 bitumen is
2 | The supplier and published list selling price for C320 bitumen is
3 | The supplier and published list selling price for polymer is
4 | The supplier and published list selling price for crumb rubber is
5 | The supplier and published list selling price for cutter is

## S8 R&F Content Factors
SCHEDULE 8 RISE AND FALL CONTENT FACTORS
COMPONENT OF WORKS | CONTENT FACTOR
| CL | CF | CM | CP | CB
For items of work which include bituminous products (i.e. spray seals and asphalt).
For all other items of work which include bituminous products (i.e. items which do not include bituminous products).

## S20 Working Time
SCHEDULE 20 WORKING TIME
I/We propose to observe the following working days and hours, vide Clause "Working Days and Hours of Work".
Working Days and Hours
Number of days to be worked per week |  | ………………………
Number of hours to be worked per day,
| Monday to Friday | ………………………
| Saturday | ………………………
| Sunday | ………………………
Starting Time
| Monday to Friday | …………………a.m.
| Saturday | …………………a.m.
| Sunday | …………………a.m.
Finishing Time
| Monday to Friday | …………………p.m.
| Saturday | …………………p.m.
| Sunday | …………………p.m.
Rostered Days Off |  | ………………………
………………………

## S23 Undertaking of Compliance
SCHEDULE 23 UNDERTAKING OF COMPLIANCE
Declaration of Compliance with the National Code of Practice for the Construction Industry and the Australian Government Implementation Guidelines, August 2009. Name of project tendered for: DPTI [XXCxxx The ..............................................
Name of Tenderer, ABN and ACN:
………………………………………………………………………………………
1 | The Tenderer confirms that it has complied with the National Code of Practice for the Construction Industry (Code) and the Australian Government Implementation Guidelines for the National Code of Practice for the Construction Industry, August 2009 (Guidelines), in preparing this Tender.
2 | The Tenderer undertakes that it complies with Code and Guidelines, and has complied with the Code and Guidelines from the time of lodgement of this tender, and that it will require compliance by its related entities (see Section 3.5 of the Guidelines).
3 | The Tenderer undertakes to ensure compliance from all subcontractors and consultants engaged on this project, should it be the successful Tenderer. All contracts must expressly require compliance with the Code and Guidelines.
4 | The Tenderer agrees that it and its subcontractors and its related entities will provide the Commonwealth or any person authorised by the Commonwealth, including a person occupying a position in the Office of the Australian Building and Construction Commissioner, with access to:
(a) inspect any work, material, machinery, appliance, article or facility;
(b) inspect and copy any record relevant to the Project and Works the subject of this Contract;
(c) interview any person; and
(d) any document requested under this contract. The document must be provided within the period specified either in person, by fax or by post,
as is necessary to demonstrate its compliance with the Code and Guidelines.
5 | The Tenderer acknowledges that it is aware the Commonwealth or Minister for Employment and Workplace Relations may impose a sanction on a Tenderer or Contractor that does not comply with the Code and Guidelines
The sanction imposed may include but is not limited to:
(a) the reporting of the breach to an appropriate statutory body or law enforcement agency (if there is evidence that the breach may also be a breach of a Commonwealth or State law), or industry association;
(b) issuing of a formal warning that future breaches may lead to more significant sanctions;
(c) preclusion from Tendering for any Commonwealth funded building and construction work for a specified period;
(d) communication of sanction details to all Commonwealth agencies to ensure a ‘whole-of-Government’ approach;
(e) publication of details of the breach and identification of the party committing the breach; and
(f) a reduction in the number of tendering opportunities that are given (see Section 8.2.2 of the Guidelines).
6 | The Tenderer is to select which of the following clauses in italics is appropriate and delete the remaining clause:
a) The Tenderer hereby gives its consent, and confirms that its related entities give their consent, to disclosure by the Commonwealth, its agencies and ministers, of information concerning the Tenderer’s and its related entities’ compliance with the Code and Guidelines and whether or not a sanction has been imposed on the Tenderer and/or related entity of the Tenderer, for the exercise of their statutory and portfolio responsibilities (the Purposes).
OR
b) The Tenderer has previously given its consent, and confirms that its related entities have previously given their consent, to disclosure by the Commonwealth, its agencies and ministers, of information concerning the Tenderer’s and its related entities’ compliance with the Code and Guidelines and whether or not a sanction has been imposed on the Tenderer and/or a related entity of the Tenderer for the exercise of their statutory and portfolio responsibilities (the Purposes), and confirms that the Tenderer and its related entities have not revoked that consent.
7 | The Tenderer has obtained or will obtain the consent of each subcontractor and consultant proposed in its Tender to disclosure by the Commonwealth, its agencies and ministers, of information concerning the proposed subcontractors, compliance with the Code and Guidelines and whether or not a sanction has been imposed on any proposed subcontractor, for the Purposes.
8 | The Tenderer acknowledges that the consents provided in clause 6 are not limited to this Tender process as the Tenderer is expected to comply with the Code and Guidelines in future projects.
9 | The Tenderer will:
(a) Describe how the Tenderer has complied with the Code and Guidelines in the past (if the Tenderer has undertaken Australian Government funded construction work in the past) and how it will comply if successful. For example, the tenderer will:
(i) comply with the Code and Guidelines;
(ii) require compliance with the Code and Guidelines from all subcontractors before doing business with them;
(iii) apply the Code and Guidelines to privately funded projects that commence after they first lodge an expression of interest or tender for Australian Government projects if the expression of interest or tender occurs on or after 1 November 2005;
(iv) ensure that contractual documents allow for a person occupying a position in the Office of the Australian Building and Construction Commissioner to access sites, documents and personnel to monitor compliance with the Code and Guidelines, including privately funded construction sites;
(v) ensure project managers or head contractors establish appropriate processes to ensure freedom of association;
(vi) ensure there is an occupational health safety and rehabilitation (OHS&R) plan for the Project;
(vii) respond to requests for information concerning Code-related matters made on behalf of Code Monitoring Group (CMG);
(viii) where practicable, ensure contractors or subcontractors initiate voluntary remedial action aimed at rectifying non-compliant behaviour when it is drawn to their attention;
(ix) ensure that CMG secretariat is notified of any alleged breaches, voluntary remedial action taken or other Code-related matters within 21 days of the party becoming aware of the alleged breach; and
(x) be aware that and ensure that sanctions applied under the Code are enforced including the exclusion of identified parties from work opportunities in accordance with decisions advised by CMG.
(b) Where the Tenderer proposes to subcontract an element of the work, the Tenderer is either to:
(i) provide the information detailed at (a) in relation to each subcontractor; or
(ii) detail how the Tenderer intends to ensure compliance with the Code and Guidelines by each subcontractor.
(c) Ensure that where threatened or actual industrial action occurs on a project, contractors, subcontractors, consultants or project managers report such action to the Funding Agency.
(Insert additional sheets for response as necessary)
Note on B6: DPTI: Specifiers to insert contract title

## S63 Seal Design
SCHEDULE 63
INDICATIVE SEAL DESIGN RATES BASED ON NOMINAL AGGREGATE
SITE DETAILS | [9 empty] | TRAFFIC |  |  | Treatment Type | BINDER DETAILS |  |  | FABRIC DETAILS |  |  | FABRIC DETAILS |  | AGGREGATE | [5 empty] | Comments
AE No. / xxx | Road Number | Road Name | Road Section | MMP Start | MMP End | Average Width (m) | Length (m) | Lane (L1 R1.) | Texture (mm) | AADT/Lane | %CV | %EHV |  | Binder Type | Pts Add Agent | App. Rate (l/m2) | Fabric Area (m2 PF1) | Tack Appl. (l/m2) | Tack Qty (lts Binder Type) | Tack Binder Type | Tack Appl. (l/m2) | Supplied by DPTI | Size (mm) | ALD (mm) | FI (%) | Spread Rate (m2/m3) | Precoat Rate (lts/m3)
Note on I4: DPTI: Left lane (L) is that lane where the road running is increasing. Lanes are thus designated L1, L2 or R1, R2. The number 1 is assigned to the lane closest to the centre line, 2 for the next closest lane and so on.
Note on J4: DPTI: Nominal values for assessment purposes in the wheel paths unless stated otherwise e.g for pre-treatment
Note on Y4: DPTI: Actual values may not be known, nominal values supplied in tender to be used.
Note on Z4: DPTI: Actual values may not be known, nominal values supplied in tender to be used.
Note on N5: DPTI: Identify pre-treatment as separate treatment type

## IPPlan
SCHEDULE 28
SOUTH AUSTRALIAN INDUSTRY PARTICIPATION PLAN
Download the Industry Participation Policy (Standard) Plan Template,
available from:
http://dpc.sa.gov.au/south-australian-industry-participation-policy
SCHEDULE 28
SOUTH AUSTRALIAN EMPLOYMENT CONTRIBUTION TEST (METROPOLITAN)
Download the Metropolitan Employment Contribution Test Template,
available from:
http://dpc.sa.gov.au/south-australian-industry-participation-policy
SCHEDULE 28
SOUTH AUSTRALIAN EMPLOYMENT CONTRIBUTION TEST (REGIONAL)
Download the Regional Employment Contribution Test Template,
available from:
http://dpc.sa.gov.au/south-australian-industry-participation-policy
Note on A2: DPTI: Include if value: • >$1 million (Regional) or • >$4 million (Metropolitan)
Note on A13: DPTI: Include if Metropolitan work and the value is $22 000 - $4 million
Note on A25: DPTI: Include if Regional work and the value is $22 000 - $1 million