[Contract Name]

[Contract Number]

AS4122-2010

Special Conditions of Contract and Annexure

To be read in conjunction with Australian Standard General Conditions of Contract AS 41222010

Template Edition: July 2026

KNET Ref. #24701608

CONTENTS

Page

FORMAL INSTRUMENT OF AGREEMENT	4

SPECIAL CONDITIONS OF CONTRACT	7

1	INTERPRETATION AND CONSTRUCTION OF CONTRACT	7

2	CONSULTANT TO PERFORM SERVICES	10

3	CLIENT TO PAY	10

4	STANDARD OF CARE	10

5	SCOPE	10

6	CLIENT'S REPRESENTATIVE AND CONSULTANT'S REPRESENTATIVE	11

7	INFORMATION	11

8	DIRECTIONS	11

9	VARIATIONS	11

10	PAYMENT	12

11	GST	13

12	TIME	14

13	LAW AND APPROVALS	15

14	CONSULTATION AND MEETINGS	15

15	REVIEW AND ACCEPTANCE	15

16	ADVERSE EVENT	15

17	COOPERATION WITH OTHERS	15

18	KEY PERSONNEL	15

19	CONFLICT OF INTEREST	16

20	SUBCONTRACTING AND ASSIGNMENT	16

20A NOVATION	17

21	COPYRIGHT AND OTHER INTELLECTUAL PROPERTY RIGHTS	17

22	MORAL RIGHTS	17

23	CONFIDENTIALITY	17

24	SUSPENSION BY THE CLIENT	18

25	SUSPENSION BY THE CONSULTANT	18

26	TERMINATION WITHOUT CAUSE	18

27	TERMINATION DUE TO DEFAULT OF EITHER PARTY	18

28	INDEMNITY	18

29	LIMITATION OF LIABILITY	19

30	INSURANCE	20

31	INSOLVENCY	20

32	DISPUTE RESOLUTION	20

33	SERVICE OF NOTICES	20

34	SURVIVAL OF TERMINATION	21

35	GOVERNING LAW	21

36	STANDARD FORM NATURE OF CONTRACT	21

37	CONSULTANT'S CONDUCT	21

38	WORK HEALTH AND SAFETY	21

39	EVALUATION OF CONSULTANT'S PERFORMANCE	22

40	RESPECTFUL BEHAVIOUR	22

41	INDUSTRY PARTICIPATION POLICY	22

42	FAULTS IN DELIVERABLES	24

43	COLLUSIVE ARRANGEMENTS	24

44	CONSULTANT WARRANTIES	25

45	CONSULTANT'S DESIGN	26

46	WORKPLACE GENDER EQUALITY	30

47	MONTHLY REPORT	30

48	CONSULTANT AS LOCAL PROVIDER	30

49 	SECURITY	31

50 	AUDITOR GENERAL	32

51 	AUSTRALIAN GOVERNMENT AGREEMENT	32

52 	AUDIT	33

53 	OPERATION OF PROPORTIONATE LIABILITY LEGISLATION	34

ANNEXURE	35

ATTACHMENT 1 – INDUSTRY PARTICIPATION POLICY PLAN OR NOT USED

ATTACHMENT 2 – DESIGNER'S CERTIFICATE OR NOT USED

ATTACHMENT 3 – SCHEDULE OF RATES

ATTACHMENT 4 – SCOPE

ATTACHMENT 5 – DEED OF NOVATION

ATTACHMENT 6 – TENDER FORM

ATTACHMENT 7 – STATUTORY DECLARATION

Copyright

These Special Conditions adapt clauses from the Transport Infrastructure Contract by the State of Queensland (Department of Transport and Main Roads) 2017.

It is licensed by the South Australian Department for Infrastructure and Transport under a Creative Commons Attribution 3.0 Australia license: https://creativecommons.org/licenses/by/3.0/au/

# FORMAL INSTRUMENT OF AGREEMENT

AGREEMENT FOR CONSULTANCY SERVICES

[Contract Name]

[Contract Number]

AGREEMENT made the date it is executed by the last party

BETWEEN:

| CLIENT: | The Minister for Infrastructure and Transport a body corporate established pursuant to the Administrative Arrangements Act 1994 (SA) |
| --- | --- |
| Address: ABN: | Level 14, 83 Pirie Street Adelaide, South Australia 5000 92 366 288 135 |
|  | or The Commissioner of Highways a body corporate established pursuant to the Highways Act 1926 (SA) Level 9, 83 Pirie Street Adelaide, South Australia 5000 45 751 448 902 or The Rail Commissioner a body corporate established pursuant to the Rail Commissioner Act 2009 (SA) Level 9, 83 Pirie Street Adelaide, South Australia 5000 23 251 040 528 (the Client) |

AND:

| CONSULTANT: | [insert] |
| --- | --- |
| Address: | [insert] |
| ACN | [insert] |
|  | (the Consultant) |

IT IS AGREED THAT:

- The Consultant shall perform the Services and otherwise perform its obligations in accordance with the Contract.

- The Client shall pay the Consultant in accordance with the Contract.

- The Contract is comprised of the documents listed in Annexure item 3.

- In the event of conflict or inconsistency between the provisions of the Australian Standard General Conditions of Contract for Consultants (AS4122-2010) and the Special Conditions, the Special Conditions shall take precedence.

- References to the "Annexures" in AS4122-2010 shall be read as Annexures to the Special Conditions as follows:

  - Annexure Part A in AS4122-2010 is the Annexure to these Special Conditions; and

  - Annexure Part B in AS4122-2010 is these Special Conditions.

- References to "attached to these Special Conditions" shall be read as a reference to the attachments to the Special Conditions.

- This Contract constitutes the entire agreement of the parties in respect of the matters dealt with in this Contract and supersedes all prior agreements, understandings, representations or negotiations in respect of the matters dealt with in this Contract.

- Any modification to the terms of this Contract must be in writing and signed by each party.

- The Obligations of the Consultant, if more than one person, under this Contract, are joint and several and each person constituting the Consultant acknowledges and agrees that it will be causally responsible for the acts and omissions (including breach of this Contract) of the other as if those acts or omissions were its own.

- A waiver by either party in respect of a breach of a provision of the Contract by the other party is not a waiver in respect of any other breach of that or any other provision of the Contract.  The failure of either party to enforce at any time any of the provisions of the Contract shall not be interpreted as a waiver of that provision.

| SIGNED by a duly authorised officer for and on behalf of THE CLIENT in the presence of: |  |  |
| --- | --- | --- |
| Witness signature Witness name Date |  | Authorised officer signature Authorised officer name Date |
| SIGNED by THE CONSULTANT in accordance with section 127 of the Corporations Act 2001 (Cth) by two directors or by one director and the company secretary: |  |  |  |
| Director signature Director name Date |  | Director/Company Secretary signature Director/Company Secretary name Date |  |

# SPECIAL CONDITIONS OF CONTRACT

# INTERPRETATION AND CONSTRUCTION OF CONTRACT

Add the following definitions to clause 1.1:

| BCISP Act | means the Building and Construction Industry Security of Payment Act 2009 (SA); |
| --- | --- |
| Business Day | has the meaning set out in the Building and Construction Industry Security of Payment Act 2009 (SA); |
| Commencement Date | means the date the Contract becomes binding, or the date the Consultant commences the Services, whichever is earlier; |
| Consultant's Industry Participation Plan | means the Consultant's plan included at Attachment 1 to these Special Conditions; |
| Consultant’s Personnel Date for Completion | means the employees, agents, officers, subcontractors and representatives of the Consultant involved in delivering the Services; means the date stated in Item 13; |
| Deliverables | means those Documents and things required under this Contract to be handed over to the Client by the Consultant and includes plans, outputs, drawings, reports, records, sketches, photographs, designs, estimates, specifications, computer sourced codes, computer aided design and drawing files, articles, information, calculations, models and files and data produced by the Consultant in the course of the Contract, but excludes the Consultant's internal administrative records. |
| Deed of Novation | means the deed at Attachment 5 to these Special Conditions; |
| Fault | means: - a defect, error, omission in the Deliverables; or - an amendment is necessary to the Deliverables because they are inappropriate for their intended use with regard to the assumptions that the Consultant can reasonably be expected to make in accordance with sound engineering principles; |
| FOI Act | means the Freedom of Information Act 1991 (SA); |
| GST Law | has the meaning set out in A New Tax System (Goods and Services Tax) Act 1999 (Cth); |
| Industry Participation Report | means a completed report prepared by the Consultant in either the standard plan report or tailored plan report, set out at clause 41. |
| Industry Participation Reporting Period | means the period of time calculated at clause 41.3; |
| Lump Sum | means the method of payment for the Services as set out at clause 10.1A; |
| notice | means request, consent, approval, direction or other communication under or for the purposes of the Contract; |
| Obligations of the Consultant | means the obligations expressed in this Contract to be performed by the Consultant or reasonably necessary to the performance by the Consultant of this Contract; |
| otherwise at law | means in the context of claim, a claim in any legal jurisdiction, including but not limited to a claim under the Contract or for breach of contract, in tort, under statute, for a quantum meruit, for restitution based on unjust enrichment, for rectification or frustration or for any other legal or equitable remedy; |
| Provisional Sum | means a sum included in the Contract for Services or an item which is not payable unless the Client directs the Consultant to perform the related Services or item; |
| Prescribed Heads of Liability | means any liability for: (a) personal injury including sickness and death; (b) loss of or damage to tangible property; (c) infringement of any Intellectual Property Right; (d) any liability to a third party arising from: (i) a negligent or wrongful act or omission by the Consultant, its employees, agents or subcontractors; or (ii) any breach of the Consultant's contractual obligation to the Client; (e) an intentional tort; (f) a breach of trust; (g) wilful default; (h) breach of confidentiality; and (i) fraud or dishonesty, and none of the Prescribed Heads of Liability limits any of the others. |
| Program | means a statement in writing showing the dates by which, or the times within which, the various stages of the Services are to be executed or completed; |
| Project | means the project being or to be undertaken by the Client and in respect of which the Services are being provided. |
| Schedule of Rates | means the method of payment for the Services as set out at clause 10.1B; |
| Schedule of Prices | means a schedule (other than a Schedule of Rates) which provides an itemised and priced breakdown of any Services; |
| Scheduled Progress | The rate of progress to be achieved by the Consultant in carrying out the Services, such that the Consultant is proceeding with due expedition and without undue delay (other than a delay for which the Date for Completion is adjusted under the Contract), so that it will complete the Services by the Date for Completion. |
| Site | means the location of the Works; |
| subcontractor | means any contractor, consultant or supplier (including their personnel), engaged by or on behalf of the Consultant and includes any supplier or hirer of materials, plant or equipment; |
| Tax Invoice | has the meaning set out in A New Tax System (Goods and Services Tax) Act 1999 (Cth); |
| The Indemnified | has the meaning given in clause 28.1, as replaced by these Special Conditions; |
| Upper Limiting Fee | means the method of payment for the Services as set out at clause 10.1C; |
| WGE Act | means the Workplace Gender Equality Act 2012 (Cth); |
| WHS Act | means the Work Health and Safety Act 2012 (SA); |
| WHS Law | means: - the WHS Act; - any regulations made at any time under the WHS Act; - any provision of the WHS Act or regulations referred to in paragraph (b); any amendment to any of the above or any other legislation in connection with the implementation or as a consequence of the WHS Act, made at any time; |
| WHS Regulations | means the Work Health and Safety Regulations 2012 (SA); |
| Works | means any construction works which have flowed from any design works that are part of the Services; |

Delete the following definitions in clause 1.1:

| Business Day | means calendar day but excludes public holidays as defined by the governing law of this Contract and weekends; |
| --- | --- |
| Deliverables | means those Documents and things required under this Contract to be handed over to the Client by the Consultant. |

1.2 Interpretation

Add the following subclauses after clause 1.2(e):

(f) references to any party to the Contract includes references to successors or permitted assignees; (g) the words 'such as,' 'particularly,' ‘including’ and ‘includes’, and any variants of those words are not used as nor are intended to be works of limitation and will be read as if followed by the words “without limitation”; (h) unless stated otherwise, a reference to a document that is not a Contract Document (such as an Australian Standard) in this Contract is a reference to the edition of that document current at the date 14 days prior to the Consultant's submission of tender for the Contract; and (i) prices, sums of money and payments under the Contract shall be in Australian currency.

# CONSULTANT TO PERFORM SERVICES

Delete the sentence under clause 2 and replace it with the following:

2.1 The Consultant must perform the Services in accordance with this Contract. 2.2 The Consultant shall take reasonable actions to ensure that: - it has the necessary skills, and experience to complete the Services in accordance with the Contract; - its employees, subcontractors and agents have the necessary skills and experience to perform those Obligations of the Consultant which are allotted to them by the Consultant, and - in accordance with the standard of care in clause 4 the subject matter of the Services or Deliverables shall be complete, correct, free from defects and errors and appropriate for the intended use with regard to the assumptions that the Consultant can be reasonably expected to make in accordance with sound engineering principles and with a view to omitting any ambiguity.

# CLIENT TO PAY

No amendment

# STANDARD OF CARE

No amendment

# SCOPE

Add the following new subclauses after clause 5.4:

5.5 Unless specified otherwise, the Consultant is entitled to retain the original Deliverables. 5.6 Deliverables must be provided to the Client in hard copy and in electronic files. The electronic files must be in an editable format which is acceptable to the Client, and also in Portable Document Format (.pdf). 5.7 The Consultant agrees and acknowledges that the Client, in its absolute discretion, may provide the Deliverables to third parties. 5.8 The Consultant shall at all reasonable times give to the Client, or to any other persons authorised in writing by the Client, access to premises occupied by the Consultant where the Services are being undertaken and shall permit those persons to inspect the performance of the Services and anything brought into existence in association with this Contract. 5.9 The Client may at any time prior to Completion request a copy of the Deliverables in the state they are in at the time of the request and the Consultant shall promptly comply with such request.

# CLIENT'S REPRESENTATIVE AND CONSULTANT'S REPRESENTATIVE

Add the following sentence to clause 6.2:

The Consultant's representative must have the authority to make binding decisions on behalf of the Consultant and at a minimum, must be contactable by the Client at any time during normal business hours.

# INFORMATION

No amendment

# DIRECTIONS

No amendment

# VARIATIONS

Add the following subclauses after clause 9.2 as follows:

9.2A If the Consultant: - becomes aware of a potential Variation; or - considers that additional services are required and that these additional services are not within the Scope, the Consultant must as soon as practicable and before performing any additional services to which the potential Variation relates, give written notice thereof to the Client. The notice must include a description of the additional services and an estimate of the value of the Variation. The Consultant must not proceed with the varied Services unless the Client's written approval has been provided. If requested by the Client, the Consultant must provide a proposed Lump Sum or Upper Limiting Fee for the varied Services. 9.2B The Consultant agrees and acknowledges that: - the Client is not liable to make payment to the Consultant for any of the additional services referred to in clause 9.2 if the Consultant has not given written notice to the Client prior to providing the additional services; and - compliance with the requirements of clause 9.2A is a condition precedent for payment for the provision of any additional services which are not within the Scope.

Delete clause 9.3 and replace it with the following:

9.3 The Fee must be adjusted for each Variation. Unless the amount of the adjustment is agreed, the adjustment must be calculated using the following order of precedence and in accordance with 9.3A: - if the Contract prescribes specific rates or prices to be applied in determining the value of Variations, those rates or prices shall be used; - if clause (a) does not apply, then if a Schedule of Rates is identified at Item 8 and is applicable, the valuation will be made by using the Schedule of Rates, or where no rate is directly applicable, a rate calculated by inference, proportion or interpolation; and - to the extent that neither clause (a) nor (b) apply, then the valuation will be made using reasonable rates or prices. 9.3A In determining the deduction to be made for work which is taken out of the Contract, once the value of the Variation has been calculated pursuant to clause 9.3 (“calculated amount”) the value of the amount to be deducted from the Fee on account of the Variation will be reduced by 5% of the calculated amount (as an additional allowance to be retained by the Consultant as consideration for administration costs incurred).

Add the following clauses after clause 9.4:

Client Initiated Variation 9.5 The Consultant shall advise the Client of the effect which the Consultant anticipates that a proposed Variation will have on the Program and the Date for Completion, and provide an estimate of the cost (including delay costs, if any) of the proposed Variation. 9.6 If the Consultant considers that the proposed Variation cannot be reasonably implemented, the Consultant shall advise the Client of the reasons for its conclusion as soon as reasonably possible. 9.7 Where the Consultant advises that the proposed Variation can be reasonably implemented, the parties shall meet and attempt to agree on the price and timing for the proposed Variation. 9.8 Where the Client and the Consultant agree on a proposed Variation, the Client may direct the Consultant by delivery of a written Variation order, to carry out the Variation for the agreed price and according to the agreed timing. 9.9 Where: - the Client and the Consultant cannot agree upon the price and/or timing for a proposed Variation, or - the Consultant considers that the proposed Variation within a certain time (acting reasonably) cannot be reasonably implemented, the Client may direct the Consultant by delivery of a written Variation order, to carry out the Variation, which shall be valued under clause 9.3.

# PAYMENT

Add the following subclauses after clause 10.1 as follows:

10.1A For Services for which the Client has accepted a Lump Sum: - the Client will pay the Lump Sum, adjusted by any additions or deletions made pursuant to this Contract; - payment will not exceed the Lump Sum unless the Client has directed a Variation; - the Lump Sum is deemed to be full payment for the provision of all supplies, tasks, services, activities, incidentals, overheads, fees and disbursements relating to the Lump Sum part of the Contract, regardless of whether or not these are mentioned in any Schedule of Prices. If a Schedule of Prices has been provided, it will only be used for the purpose of assisting in the determination of progress payments. Unless specified otherwise, progress payments will be made as a portion of the Lump Sum commensurate with the amount of Services provided as of the date of invoice. 10.1B For Services for which the Client has accepted a Schedule of Rates: - the Client will pay the sum ascertained by multiplying the measured quantity of each item of service actually carried out under this Contract by the rate accepted by the Client for the item of service, adjusted by any additions or deletions made pursuant to this Contract; and - except where a disbursement has been specifically included in the schedules, the rates are deemed to allow for all supplies, tasks, services, activities, incidentals, overheads, fees and disbursements relating to the item of service listed in the schedule. No separate payment will be made for any work or expense required for the item of service listed in the schedule but not specifically mentioned in the description of the item of service. A change in the measured quantity provided does not entitle the Consultant to amend the applicable rate. 10.1C For work for which the Client has accepted an Upper Limiting Fee, the Client will pay an amount ascertained on the same basis as a Schedule of Rates, up to the amount of the Upper Limiting Fee. Payment will not exceed the Upper Limiting Fee unless the Client has directed a Variation that requires additional payment. 10.1D For work for which the Client has accepted a Provisional Sum, the Client will pay the amount of the Provisional Sum only if the Client directs the Consultant to perform the Services or item to which the Provisional Sum relates and the Consultant performs the Services or item.

Add a new subclause after clause 10.4 as follows:

10.4A Without limiting the effect of subclause 10.4 herein, the payment claim must: - contain full details of any approved Variations which have been completed or partially completed; - contain the estimated cost to complete the Services, including approved Variations and any anticipated future Variations that the Consultant is aware of; - contain if requested by the Client, an earned value report in accordance with AS 4817-2006 'Project Performance Measurement Using Earned Value'; and - in the case of the first payment claim and the payment claims issued at the end of each subsequent 6 month period thereafter, and the final payment claim if stated as being required in Annexure Item 37, contain a completed and true Statutory Declaration in the form of Attachment 7, executed on the date of the payment claim.

Delete clause 10.8 and replace it as follows:

10.8 Where the Consultant submits a payment claim that satisfies the requirements of clause 10.4 and clause 10.4A and the Client fails to make the payment that is due and payable in accordance with clause 10.6, the Consultant may notify the Client in writing that it will suspend performance of the Services, after expiry of at least 5 Business Days written notice to the Client. Unless the payment has been made, the Consultant may suspend performance of the Services any time after expiration of the notice period. The Consultant must promptly lift the suspension after the Client has made the payment.

Add new clauses 10.11 to 10.12 as follows:

10.11 If the BCISP Act applies to the payment claim, the Client's address for the service of notices is the address of the Client's representative or such other address advised by the Client's representative. 10.12 Unless set out in the Contract or otherwise agreed in writing, the Consultant shall be responsible for all travelling expenses, costs of consumables and office expenses incurred in providing the Services.

# GST

Delete clause 11 and replace it with the following:

11. GOODS AND SERVICES TAX 11.1 Payment from the Client to the Consultant will include the GST payable. 11.2 Any invoice for payment under this Contract shall be a Tax Invoice in accordance with the GST Law. The Client is not obliged to make any payment under this Contract unless the Consultant has provided a Tax Invoice in respect of that payment.

# TIME

Delete clause 12 and replace it with the following:

12. TIME 12.1 The Consultant shall commence the Services promptly upon execution of this Contract and shall proceed with due expedition and without delay, and complete the Services by the Date for Completion. 12.1A The Consultant must carry out the Services in accordance with Scheduled Progress. 12.1B Whenever requested, the Consultant must demonstrate to the Client that it is achieving Scheduled Progress. 12.1C For these purposes and without limiting the generality of the foregoing, the Consultant shall be obliged, in consultation with the Client’s Representative, to take such positive steps to re-schedule, re program, expedite and adjust activities, sequences and the carrying out and execution of the Services generally so as to ensure that Scheduled Progress is maintained. 12.1D If the Consultant is not achieving Scheduled Progress, the Client may instruct the Consultant to take all reasonable steps to achieve Scheduled Progress, at the Consultant’s cost. Programs 12.2 The Client may direct the Consultant to furnish to the Client a Program within the time and in the form directed by the Client. The Program must include a schedule of key dates, which can be adjusted at the Client’s request. The Consultant shall not, without reasonable cause, depart from: - a Program included in the Contract; or - a Program furnished to the Client. 12.3 The Consultant may voluntarily furnish a Program to the Client at any time. A Program shall not affect the rights or obligations in this clause 12, including the obligation not to depart from an earlier Program. 12.4 A Program does not form part of the Contract and shall only be used for the purpose of enabling the Client to monitor the progress of the Consultant in the provision of the Services. Delay 12.5 Within 10 Business Days of it becoming evident to the Consultant that anything, including an act or omission of the Client, Client's employees, consultants, subcontractors or agents may delay the Consultant, the Consultant shall notify the Client in writing with details of the possible delay and the cause. The notice shall be endorsed 'Consultant's Notice of Possible Delay Under Clause 12.5'. 12.6 When it becomes evident to the Client that anything which the Client is obliged to do or provide under the Contract may be delayed, the Client shall give notice to the Consultant in writing of the extent of the likely delay. 12.7 If the Consultant is, or will be delayed in, reaching the Date for Completion by a cause identified in clause 12.5 or Item 14 and within 20 Business Days after the commencement of that cause the Consultant gives the Client a written claim for an extension of time to the Date for Completion endorsed 'Consultant's Extension of Time Claim Under Clause 12.7' and setting out the facts on which the claim is based subject to clause 12.7A, the Consultant shall be entitled to an extension of time to the Date for Completion. 12.7A If the Consultant provides a notice under clause 12.7, and satisfies the Client that all the following conditions apply: (a) the cause of the delay was a cause identified in clause 12.5 or Item 14; (b) the cause of the delay was beyond the control of the Consultant; (c) the Consultant has taken all reasonable steps to avoid and minimise the delay and its effects; and (d) the Consultant have given to the Client notice required under clause 12.7, the Consultant will be entitled to an extension of time to the Date for Completion for the number of days assessed by the Client. 12.8 With any claim for an extension of time to the Date for Completion, or as soon as practicable thereafter, the Consultant shall give the Client written notice of the number of days extension claimed. 12.9 If the Consultant is entitled to an extension to the Date for Completion, the Client shall within 10 Business Days after receipt of the notice of the number of days extension claimed, grant a reasonable extension of time. If within the 10 Business Days the Client does not grant the full extension of time claimed, the Client shall, before the expiration of the 10 Business Days, give the Consultant notice in writing of the reason. 12.10 Where an extension of time is granted following notice under clause 12.7, and the delay is caused solely by the Client, the Consultant may apply for a Variation under clause 9 of the Contract as if the extension of time was a Direction by the Client. Where the Client agrees that a Variation is appropriate and that the Variation will involve the Consultant incurring additional cost, the following shall apply: (a) the additional cost payable by the Client shall be determined by agreement or in accordance with clause 9.3; and (b) the cost determined under clause 12.10(a) shall be payable after completion of the Services and only if completion of the Services was actually delayed for the number of days assessed by the Client when granted the relevant extension of time. 12.11 Notwithstanding that the Consultant is not entitled to or not claimed an extension of time the Client may at any time and from time to time by notice in writing to the Consultant extend the Date for Completion for any reason.

# LAW AND APPROVALS

No amendment

# CONSULTATION AND MEETINGS

No amendment

# REVIEW AND ACCEPTANCE

No amendment

# ADVERSE EVENT

No amendment

# COOPERATION WITH OTHERS

No amendment

# KEY PERSONNEL

Add the following paragraphs to clause 18:

The key personnel (including any subcontractor’s key personnel) nominated in the Consultant's tender must perform the Services, unless they are on leave or have resigned from the Consultant's or subcontractor’s employment. The skills and experience of the alternative personnel must not be less than the personnel that they are replacing. The Consultant acknowledges and agrees that: - there is no contract of any nature in existence pursuant to this Contract between the Client and any person employed or engaged by the Consultant for the purposes of this Contract; - the Consultant is liable for all remuneration, claims and other entitlements payable to the Consultant's Personnel; and - the Consultant is responsible for complying with the requirements with the Income Tax Assessment Act 1936 (Cth) pursuant to this Contract to the extent that the Client is not thereby required to make PAYE deductions from any amount payable for the Services. The Consultant indemnifies the Client and must keep the Client indemnified against any claims by any person who is employed by or is an agent of the Consultant that it may be held or asserted that a relationship of employer and employee has been created under this Contract. If the Client forms the reasonable opinion that any of the Consultant's Personnel do not have the capacity to adequately undertake the tasks to be performed pursuant to this Contract or do not maintain the standard of work required by this Contract or are responsible for any disruption of work being undertaken as part of this Contract, the Client may notify the Consultant accordingly, and thereupon such Consultant's Personnel must be withdrawn from undertaking further work involved in the Services.

# CONFLICT OF INTEREST

Delete clause 19.4 and replace it as follows:

19.4 The Consultant must immediately notify the Client of any conflict of interest or any circumstances which may give rise to a conflict of interest for the Consultant in respect of the Contract and comply with any reasonable direction of the Client with respect to such conflict of interest.

Add the following subclauses after clause 19.5 as follows:

19.6 The Consultant must not permit or contribute to any publicity in respect of the Contract or any related matter unless the Consultant has obtained the Client's approval. 19.7 For the avoidance of doubt, a conflict of interest includes a potential, actual or perceived conflict of interest.

# SUBCONTRACTING AND ASSIGNMENT

Add the following new clauses after clause 20.4:

20 ASSIGNMENT AND THE ENGAGEMENT OF SUBCONTRACTORS 20.5 The Consultant must enter into subcontracts with subconsultants on the same terms and conditions as this Contract (other than clause 52 (Audit) which may be deleted at the Consultant’s discretion) without changing the intent or effect, subject only to such amendments and appropriate changes in detail as are necessary to reflect the conditions of that subcontract. 20.6 The Client may assign the Contract to another Minister of the Crown in right of the State of South Australia by notice to the Consultant. 20.7 The Client may require subconsultant work to be undertaken by professional service contractors registered in the Department for Infrastructure and Transport Building and Construction Project Prequalification System (the Department Prequalification System) and if required the Consultant must ensure that the designated subconsultant work is undertaken by professional service contractors registered in the Department Prequalification System. 20.8 Without limiting the foregoing, the Consultant must ensure that all subcontracts include payment provisions which reflect that the Consultant must pay the Subcontractor within (and by no later than) 15 days from the date of submission of a claim for payment.

# 20A NOVATION

Add a new clause 20A as follows:

20A NOVATION 20A.1 If the Client wishes to novate this Contract to another South Australian Government entity, the Client will issue a written request to the Consultant. 20A.2 Within 5 Business Days of a request from the Client in accordance with clause 20A.1, the Consultant must, at its own cost enter into a deed of novation in substantially the same form as the Deed of Novation.

# COPYRIGHT AND OTHER INTELLECTUAL PROPERTY RIGHTS

Add a new clause 21.7 as follows:

21.7 The Consultant releases and indemnifies the Client from and against all actions which may be brought or made against the Client by any person, including the Client, arising from any infringement or alleged infringement of any Intellectual Property Rights or moral rights in respect of the Deliverables.

# MORAL RIGHTS

No amendment

# CONFIDENTIALITY

Delete clause 23.1 and replace it as follows:

23.1 Subject to clause 23.2, the Consultant must treat as confidential: - all Documents generated by this Contract; and - all other information which of its nature is confidential or which the Consultant ought reasonably to know is confidential. The Client is not obliged to treat the Deliverables as confidential, but will treat other Documents as confidential.

Delete clause 23.3 and replace it as follows:

23.3 The Consultant must not publish or enable others to publish any information connected with the Services or this Contract without the consent of the Client which, which may be withheld at the Client's sole and unfettered discretion.

Add a new clause 23.5 as follows

23.5 The Consultant agrees to disclosure of this Contract in accordance with Department of Premier and Cabinet Circular 27 (PCO27) 'Disclosure of Government Contracts'. The Consultant's attention is drawn to the FOI Act. No exemption from the provisions of the FOI Act applies to this Contract.

# SUSPENSION BY THE CLIENT

Delete clause 24.4 and replace it with "Not Used."

# SUSPENSION BY THE CONSULTANT

No amendment

# TERMINATION WITHOUT CAUSE

No amendment

# TERMINATION DUE TO DEFAULT OF EITHER PARTY

Add the following subclauses after 27.2(d):

- the Consultant fails to observe or perform a material Obligation of the Consultant or the work performed by the Consultant is otherwise unsatisfactory to the Client (in the Client's reasonable opinion); - the Consultant fails to comply with a Direction of the Client given in accordance with the provisions of the Contract; - the Consultant assigns any of its benefits or purports to assign, sub-let or otherwise divest itself of any of the Obligations of the Consultant without the written consent of the Client; - the Consultant abandons or refuses to proceed with the supply of Services whether or not it has commenced work; - the Consultant is not able to reasonably satisfy the Client that the Consultant will be able to complete the Services by the Date for Completion or reach previously agreed significant milestones; - failing to comply in part or in whole with the requirements of subclause 48.2 to 48.7 (inclusive) in relation to Local Providers; or - significantly failing to achieve Scheduled Progress..

Add a new clause 27.5 as follows:

27.5 On expiry, termination or frustration of the Contract, the Consultant must promptly deliver to the Client the Deliverables produced by the Consultant in the course of the Contract (including any incomplete Deliverables and any materials which have been prepared by the Consultant which would have formed part of the Deliverables had the Contract not been terminated or frustrated and the Consultant had met its obligations under the Contract).

# INDEMNITY

Delete clauses 28.1 and 28.2 and replace it with the following:

28.1 The Consultant releases and indemnifies the Client and the Client's employees and agents ("The Indemnified") from and against all actions whatsoever which may be brought or made against The Indemnified by any person, including the Consultant, arising, directly or indirectly from: - any breach of a duty owed in a professional capacity in connection with the performance of the Services by the Consultant or its subcontractors, or any person for whose conduct the Consultant is liable; - any other negligent professional act, error or omission on the part of the Consultant, or any person for whose conduct the Consultant is liable, arising out of the performance (or attempted or purported performance or non-performance) of the Services by the Consultant; - any contravention of any Legislative Requirements or any unlawful or negligent act or omission by the Consultant, its agents or its subcontractors, or any person for whose conduct the Consultant is liable; - any unlawful or negligent act or omission of the visitors, invitees or licensees of the Consultant; - any death, personal injury, loss or damage suffered by the Client or the Consultant (or any of its subcontractors, employees, agents, visitors, invitees or licensees) or any other person, arising from an unlawful or negligent act or omission of the Consultant in the course of the performance (or attempted or purported performance) of the Contract; - any loss of or damage to tangible property caused or contributed by the unlawful or negligent act or omission of the Consultant, its agents or its subcontractors or any person for whose conduct the Consultant is liable; or - any breach of this Contract by the Consultant. 28.2 The indemnity in this clause 28 shall not apply to: - exclude any other right of the Client's to be indemnified by the Consultant, or - claims in respect of the Client's right to have the Services carried out; and/or - the extent that the Client fails to act reasonably to mitigate the liability, loss or damage, cost or expense.

# LIMITATION OF LIABILITY

Delete clause 29 and replace it with the following:

29. LIMITATION OF LIABILITY 29.1 Limitation - Except for any liability in respect of the Prescribed Heads of Liability (which remain unlimited), the Client and the Consultant agree to limit the liability of either party to the other party to the amount equal to the greater of the Fee or the amount of the relevant insurance that the Consultant is required to maintain under this Contract regardless of what the Client is indemnified for or actually recovers. - The liability of a party for loss or damage sustained by the other party will be reduced to the extent that such loss or damage has been caused by the other party’s breach of contract, act, omission or negligence. 29.2 Exclusion of Liability A party will not be liable to the other party for: - loss of business opportunity; - loss of goodwill; - loss of profit; - loss of contracts; - loss arising from business interruption; - loss of or corruption of data; - loss of anticipated savings; - loss of revenue; - the cost of capital or other financing costs; or - loss of production, which loss or cost arises due to the party's breach of this Contract, act, omission or negligence. 29.3 Priority of Clause 29 In resolving inconsistencies in the Contract, the provisions of this clause 29 shall take priority.

# INSURANCE

No amendment.

# INSOLVENCY

No amendment

# DISPUTE RESOLUTION

No amendment

# SERVICE OF NOTICES

Delete clause 33 and replace it as follows:

33 SERVICE OF NOTICES 33.1 A notice, shall be in writing, in English and addressed to the receiving party, and either: - sent by registered post to or left at the address specified in Item 29; - handed to the other party's representatives identified in clause 6 and Item 6 or Item 7; - sent by email to the email address specified in Item 29, or - sent via a proprietary document management system which the parties have agreed in writing may be used for the purpose of giving a notice under the Contract. 33.2 A notice is deemed to have been received: - if sent by registered post, on the third Business Day (or the 10th Business Day if posted to or from a place outside Australia) after posting; - if delivered personally, upon delivery - if sent by email: - on a Business Day, on dispatch of the transmission, or - on a day other than a Business Day, on the next Business Day, unless the sender's server indicates a malfunction or error in transmission or the recipient immediately notifies the sender of an incomplete transmission, or - if sent via any proprietary document management system which the parties have agreed may be used for the purpose of giving a notice under the Contract, upon notification from that system to the recipient of the notice having been delivered on the proprietary document management system. 33.3 A party may specify another address or email address for the purposes of this clause 33, by notice to the other party. 33.4 Any notice served after 5pm on any Business Day or on a day which is not a Business Day is deemed to be served on the next Business Day. 33.5 Service of payment claims under the BCISP Act by the Consultant on the Client shall be made by forwarding or serving such claims to the Client's representative identified at Item 6.

# SURVIVAL OF TERMINATION

No amendment

# GOVERNING LAW

No amendment

# STANDARD FORM NATURE OF CONTRACT

Delete this clause and replace it with "Not Used."

# CONSULTANT'S CONDUCT

Add the following new clause 37:

37. CONSULTANT'S CONDUCT 37.1 The Consultant represents and undertakes to the Client that it will conduct itself in a manner that does not invite, directly or indirectly, the Client's officers, employees or agents or any public sector employee (as defined in the Public Sector Act 2009 (SA)) to behave unethically, to prefer private interests over the Client's interests or to otherwise contravene the Code of Ethics for the South Australian Public Sector. 37.2 The Client is a public authority for the purposes of the Independent Commissioner Against Corruption Act 2012 (SA) (“ICAC Act”). For the term of the Contract the Consultant is considered a public officer under the ICAC Act and must comply with the ICAC Act and the directions and guidelines published by the Independent Commissioner Against Corruption. 37.3 The Consultant must comply with the Code of Practice for the South Australian Construction Industry. Lodgement of a tender will be evidence of the Consultant’s agreement to comply with the Code for the duration of any resulting contract that may be awarded. If any Consultant fails to comply, the failure will be taken into account by the Government of South Australia and its Agencies when considering this or any subsequent tender by the Consultant and may result in such tender being passed over and or a change in the status of the Consultant on any South Australian Government register of consultants.

# WORK HEALTH AND SAFETY

Add the following new clause 38:

38 WORK HEALTH AND SAFETY ## The Client is committed to the provision of a healthy and safe working environment and expects the Consultant to demonstrate the same level of commitment to work health and safety. The Consultant must ensure all Services are carried out safely and in a manner that does not put the health and safety of persons at risk and comply with the WHS Law. ## If requested by the Client, the Consultant must provide: - evidence satisfactory to the Client of its capacity to comply with the WHS Act; - evidence that its personnel, agents and subcontractors have received appropriate training in and are aware of their legal obligation and responsibilities in relation to work health and safety; and - the Consultant’s registration number with the Return to Work Corporation. ## The Consultant must when on the premises occupied by the Client and when using the Client’s facilities, comply with the Client's work health and safety policies, directions, procedures and instructions relating to work health and safety that are in effect at those premises and facilities. ## The Consultant must comply with its duty under the WHS Law to consult, cooperate and coordinate activities with all persons who have a work health and safety duty in relation to the same matter. ## If the Consultant becomes aware of any potentially hazardous situation on the premises of the Client, the Consultant must immediately bring it to the Client's attention for a Direction regarding the matter.

# EVALUATION OF CONSULTANT'S PERFORMANCE

Add the following new clause 39:

39. EVALUATION OF CONSULTANT'S PERFORMANCE The Client may undertake an ongoing evaluation of the Consultant's performance in providing the Services and compliance with the requirements of this Contract. A copy of any such evaluation will be forwarded to the Consultant. If the Consultant disagrees with the evaluation, it may forward a request to the Client for a review, along with reasons why it should be reviewed. The Client's decision will then be final. The evaluation may be taken into account in the assessment of future tenders with the Client or other government agencies.

# RESPECTFUL BEHAVIOUR

Add the following new clause 40:

40. RESPECTFUL BEHAVIOUR The Consultant acknowledges the Client's zero tolerance towards gender based violence, discrimination and all forms of unacceptable behaviours in the workplace and the broader community. The Consultant agrees that, in performing the Works, the Consultant's Personnel will at all times: - act in a manner that is non-threatening, courteous, and respectful; and - comply with any instructions, policies, procedures or guidelines issued by the Client regarding acceptable workplace behaviour. If the Client believes that the Consultant's Personnel are failing to comply with the behavioural standards specified in this clause, then the Client may in its absolute discretion: - prohibit access by the relevant Consultant's Personnel to the Client's premises; and - direct the Consultant to withdraw the relevant Consultant's Personnel from providing the Services.

# INDUSTRY PARTICIPATION POLICY

Add the following new clause 41:

41. INDUSTRY PARTICIPATION POLICY This clause 41 only applies if stated in Annexure Item 32. Agencies and private parties contracting to the Government of South Australia are required to comply with the South Australian Industry Participation Policy (SAIPP) and the supporting procedural and reporting requirements. ## The Consultant must implement the Consultant’s Standard or Tailored Industry Participation Plan (“SIPP” or “TIPP”) approved by the Industry Advocate (“IA”) in Attachment 1 to these Special Conditions. ## The Consultant must provide an Industry Participation Report (“IPP Report”) in respect of each Industry Participation Reporting Period to the IA within two weeks of the end of each period, in the form set out at https://www.industryadvocate.sa.gov.au/policy-and-resources. ## An Industry Participation Reporting Period is: ### the period between the Commencement Date and the date six (6) months after the Commencement Date; ### each subsequent 6 month period during the term of the Contract; ### if the Contract ends on a date other than an anniversary of the Commencement Date or an anniversary of the date in 41.3(a), the period from the conclusion of the preceding Industry Participation Reporting Period until the date of termination or expiry of the Contract; ### for short-term projects of strategic importance to the State, the period notified by IA to the Consultant in writing; and ### where the term of the Contract is for a period less than 6 months, the term of the Contract. ## The Consultant must attend any meeting scheduled by the IA during the term of the Contract to review how the SIPP or TIPP is being implemented and advanced, and for this purpose, the Consultant must provide all information reasonably requested by the IA. The IA must give the Consultant not less than ten (10) Business Days’ notice of any such meeting. ## The IA may, by written notice require that the Consultant within a reasonable time specified in the notice, provide information or documents to enable the IA to assess the Consultant’s compliance with this clause 41. ## If the IA reasonably believes that the Consultant is not complying with the requirements of this clause 41, the IA may by notice in writing direct that the supply comply with those requirements. ## Upon receipt of the notice, if the Consultant is of the opinion that its noncompliance is reasonable and justified, the Consultant may provide a response to the IA outlining that opinion and the reasons for it. ## The Consultant’s failure to comply, in whole or in part, with the commitments contained within the SIPP or TIPP will be a factor taken into account in the award of future contracts for the Government of South Australia. ## In this clause, “Industry Advocate” or “IA” means the person from time to time appointed by the Governor to the position of Industry Advocate under s.5 of the Industry Advocate Act 2017.

# FAULTS IN DELIVERABLES

Add the following new clause 42:

42. FAULTS IN DELIVERABLES 42.1 If it is necessary to subsequently amend the Deliverables due to a Fault, then the Consultant shall rectify the relevant Deliverables and shall be responsible for that part of the cost, including Client's costs, of rectifying the Deliverables which may reasonably be attributed to the Consultant, its employees, subcontractors or agents. 42.2 As soon as possible after discovery of the Fault, where there do not appear to be any construction rectification cost implications, the party that identified the Fault will notify the other party of the Fault. 42.3 Where Works results from the Deliverables, and a Fault is subsequently discovered after construction, the following will apply: - as soon as possible after discovery of the Fault, the party that identified the Fault will notify the other party; - following notification in (a) above, except in cases of urgency, the Client shall provide the Consultant an opportunity to respond to the existence of the Fault and, where agreement is reached, the Consultant shall prepare or be involved in the preparation of details of the rectification work to be performed, so that the Consultant has the opportunity to minimise the costs and delays resulting from rectification works. Such response by the Consultant shall be within 3 Business Days of receipt of the notice in (a) above; - where agreement is not reached within 5 Business Days of the notice in (a) above or where urgency precludes the opportunity for Consultant response, the Client shall carry out the rectification work and the costs shall become a debt due and owing to the Client by the Consultant, payable within 30 days if requested by the Client; and - to the degree to which the Consultant, its employees and agents were responsible for the Fault, the Consultant will be responsible for the reasonable cost of rectification works including costs of delays associated with the rectification works. 42.4 Any omission by the Client to require revision or amendment of any Deliverables shall not constitute an acknowledgment or admission that such Deliverables is correct in detail as to measurement dimensions materials or in any other particular, the responsibility for which shall remain the Consultant’s. Nothing the Client does or omits to do in connection with the Deliverables makes the Client responsible for the Deliverables, or prevents the Client from relying on or enforcing any right under the Contract or otherwise.

# COLLUSIVE ARRANGEMENTS

Add the following new clause 43:

43. COLLUSIVE ARRANGEMENTS The Consultant warrants and represents to the Client that: - it had no knowledge of any offered or tendered fee or price of any other tenderer or offerer for the Services at the time of the tender or offer; - except as disclosed in its tender or offer, it has not entered into any contract, arrangement or understanding to pay or allow to be paid any money directly or indirectly to a trade or industry association (above the published standard membership fee) or to or on behalf of any other tenderer or offerer in relation to its tender or offer for this Contract, nor paid or allowed to be paid any money on that account; - except by prior agreement with the Client, it has not paid or allowed to be paid or entered into any contract, arrangement or understanding to pay or allow to be paid any money directly or indirectly to or on behalf of any other tenderer or offerer nor received any money or allowance from or on behalf of any other tenderer in relation to its tender or this Contract, nor will it pay or allow or receive any such money, and - if, without the Client's prior agreement, it receives or has received any money or allowance from any other offerer or tenderer in relation to its tender, the other tenderer's tender or this Contract, then without prejudice to any other right or remedy of the Client, such money or allowance shall be deemed to be held by the Consultant on trust for the Client and shall be paid to the Client immediately.

# CONSULTANT WARRANTIES

Add the following new clause 44:

44.1 The Consultant warrants that it has and it shall be deemed to have: - examined carefully and to have acquired actual knowledge of the contents of the Contract Documents, the Client's requirements, the tender documents and any other information made available in writing by the Client or any other person on the Client's behalf to the Consultant for the purpose of preparing and submitting the Consultant's tender; - examined all information relevant to the risks, contingencies and other circumstances which could affect the Consultant's tender and which was obtainable by the making of detailed enquiries; - informed itself of the nature of the work and materials necessary for the execution of the Services; - satisfied itself as to the correctness and sufficiency of the Fee and that the Fee covers the cost of complying with all its obligations under the Contract and of all matters and things necessary for the due and proper performance and completion of the Services; - informed itself of all requirements of any government authorities in relation to the Services generally; - obtained all appropriate professional and technical advice on all matters and circumstances with respect to the matters referred to in this cluse prior to submitting its tender for the Services, and - entered into this Contract based on its own investigations, interpretations, deductions, information and determinations and the Consultant acknowledges that it is aware that the Client has entered into the Contract relying upon this acknowledgment and warranty. 44.2 Failure by the Consultant to do all or any of the things it is deemed to have done under this clause will not relieve the Consultant of any of its obligations or liabilities under the Contract, including its obligation to perform and complete the Services in accordance with the Contract. Clause 44.3 shall only apply if the Services are not design related and Item 31 states that clause 45 does not apply. 44.3 Consultant's warranties The Consultant further warrants that: - it shall at all times be suitably qualified and experienced, and shall exercise due skill, care and diligence in the performance of the Services; - the Services will be carried out and completed in accordance with the requirements of the Contract, and that such Services: - will satisfy the Client's Requirements and be fit and adequate for the purposes stated in, or that can be reasonably implied from the Contract, and suitable and adequate for the Project; and - will be provided using good industry practices; and - will comply with the standards and other requirements specified by this Contract, including all Legislative Requirements and the requirements of all government authorities. 44.4 Consultant's liabilities, obligations and warranties unaffected The warranties in clause 44.3 shall remain unaffected, notwithstanding: - any Services that may have been carried out by, or on behalf of, the Client; - any comment upon, response to, review or acceptance of, giving or withholding of permission to use, approval to proceed with, Direction or query in relation to or request to vary any of the Services, by the Client, or any agent, employee or consultant of the Client; - any acceptance of the Services; - any variation directed or approved by the Client in accordance with clause 9, or - the provision of any warranty.

# CONSULTANT'S DESIGN

ADD a new clause "45 CONSULTANT'S DESIGN" as follows:

45 CONSULTANT'S DESIGN This clause 45 shall only apply if stated to apply at Item 31. The parties agree that the Client may act in its absolute discretion when exercising any of its rights under clause 45. 45.1 Definitions Unless the context requires otherwise, in this clause 45 and any other part of the Contract relating to work to be designed by the Consultant: - 'Consultant's Construction Drawings' means the drawings prepared by, or on behalf of, the Consultant which are necessary for the construction and/or installation of the Works. - 'Consultant's Construction Specifications' means the specifications prepared by, or on behalf of, the Consultant which are necessary for the construction and/or installation of the Works. - 'Consultant's Design' means the design for the Works which has been accepted pursuant to clause 45.7(d) or is deemed to have been accepted pursuant to clause 45.9 and includes: - the Deliverables; - the Consultant's Construction Drawings, the Consultant's Construction Specifications and all other drawings, specifications, manuals, designs (including systems designs) and other information, calculations, samples, models, patterns and the like, and - any new software and any customised, modified or extended parts of any existing software (including associated data and documentation) required for the construction and/or installation of the Works or which the Contract requires the Consultant to create or cause to be created or to provide (in all forms, including electronic) and which has become the Consultant's Design in accordance with clause 45.10. - 'Designer's Certificate' means a certificate in the form of Attachment 2 to these Special Conditions. - 'Client's Requirements' means any written summary or outline of the Client's requirements for the Services, Deliverables and Works provided by the Client. 45.2 Consultant's warranties The Consultant warrants that: - it shall at all times be suitably qualified and experienced, and shall exercise due skill, care and diligence in the execution and completion of the design of the Works; - the design of the Works will be carried out and completed in accordance with the requirements of the Contract, and that: - such design will satisfy the Client's Requirements and be fit and adequate for the purposes stated in, or that can be reasonably implied from the Contract, and suitable and adequate for the Site; and - construction in accordance with such design will comply with the standards and other requirements specified by this Contract, and - the Works will, if constructed in accordance with the Consultant's Design: - satisfy the Client's Requirements and be fit and adequate for the purposes stated in, or that can be reasonably implied from, the Contract and be suitable and adequate for the Site; and - comply with all the requirements of the Contract, including all Legislative Requirements and the requirements of all government authorities. 45.3 Consultant's liabilities, obligations and warranties unaffected The warranties in clause 45.2 shall remain unaffected, notwithstanding: - any design work in respect of the Works may have been carried out by, or on behalf of, the Client; - any comment upon, response to, review or acceptance of, giving or withholding of permission to use, approval to proceed with, Direction or query in relation to or request to vary any Consultant's Construction Drawing or Consultant's Construction Specification or any part of the quality assurance system (in so far as it relates to the Works), by the Client, or any agent, employee or consultant of the Client; - any acceptance of a drawing or specification pursuant to clause 45.7(d) or deemed acceptance pursuant to clause 45.9; - any variation directed or approved by the Client in accordance with clause 9, or - the provision of any warranty. 45.4 The Design The Consultant shall ensure the Consultant's Design is carried out and completed in accordance with the Contract and that the Consultant's Design, the Consultant's Construction Drawings and the Consultant's Construction Specifications: - are in accordance with the Client's Requirements; - are consistent with the Consultant's tender for the Services (except to the extent that the Consultant's tender is inconsistent with the Client's Requirements or the Contract Documents or provides for standards of finish, workmanship or materials of a lesser standard than that required by the Client's Requirements or the Contract Documents, in which case the Consultant's Design shall be in accordance with the Client's Requirements and the Contract Documents), and - are sufficient to enable the Client to construct and complete the Works. 45.5 Submission of Consultant's Construction Drawings, Specifications and certificate The Consultant shall, in accordance with the Program, submit to the Client: - one copy of the Consultant's Drawings and Consultant's Specifications for the Works or as otherwise directed by the Client, and - with the copy of the Consultant's Drawings and Consultant's Specifications for the Works submitted under clause 45.5(a), one copy of a Designer's Certificate (signed by a principal of the Consultant). 45.6 No obligations to review or check Drawings and Specifications The Client is not required to review or check any Consultant's Drawings or Consultant's Specifications submitted by the Consultant under clause 45 or any reasons or supporting information submitted by the Consultant under clause 45: - for errors, omissions or compliance with the Contract (including the Client's Requirements), or - for any other purpose whatsoever. The Consultant acknowledges that in considering and responding to any Consultant's Drawings or Consultant's Specifications submitted by the Consultant (if any such consideration occurs or response is given), the Client will be relying upon: - the advice, skill and judgment of the Consultant; - the Designer's Certificate provided under clause 45.5 - any reasons and supporting information given by the Consultant under clause 45, and - the warranties given by the Consultant under the Contract. No review of, comments upon, rejection of, or failure to review or comment upon or reject, any Consultant's Drawings or Consultant's Specifications submitted by the Consultant or any other direction by the Client about such Consultant's Drawings or Consultant's Specifications forming part of the Consultant's Design will: - relieve the Consultant from, or alter or affect, the Consultant's liabilities or responsibilities whether under the Contract or otherwise according to law, or - prejudice the Client's rights against the Consultant whether under the Contract or otherwise according to law. 45.7 Giving and withholding permission to use Within 10 Business Days after the submission by the Consultant to the Client of: - Consultant's Drawings and Consultant's Specifications and the accompanying Designer's Certificate in accordance with clause 45.5; - resubmitted Consultant's Drawings and Consultant's Specifications and the accompanying Designer's Certificate in accordance with clause 45.8(a), or - reasons and supporting information in accordance with clause 45.8(b) concerning Consultant's Drawings and Consultant's Specifications for which the Client has previously withheld permission to use; as the case may be, the Client may either: - give the Consultant notice in writing that it accepts use of the relevant Consultant's Drawings and Consultant's Specifications for the construction of the Works, or - advise the Consultant in writing that it does not accept such Consultant's Drawings or Consultant's Specifications and give the Consultant brief reasons for withholding permission. 45.8 Where permission to use is withheld If the Client advises the Consultant under clause 45.7(e) that it does not accept the Consultant's Drawings or Consultant's Specification, the Consultant shall either: - amend the Consultant's Drawing or Consultant's Specification and resubmit it to the Client together with an accompanying Designer's Certificate in accordance with clause 45.5, or - submit written reasons and supporting information to the Client stating why use of the Consultant's Drawing or Consultant's Specification should be accepted. 45.9 Deemed permission to use If within 10 Business Days after submission by the Consultant to the Client of: - a Consultant's Drawing or Consultant's Specification and the accompanying Designer's Certificate in accordance with clause 45.5; - a resubmitted Consultant's Drawing or Consultant's Specification and the accompanying Designer's Certificate in accordance with clause 45.7(a); or - reasons and supporting information in accordance with clause 45.7(b) concerning a Consultant's Drawing or Consultant's Specification for which the Client has previously withheld permission to use, as the case may be, the Client has not responded to the Consultant as provided in clause 45.7(d) or 45.7(e), then upon the expiration of the relevant 10 Business Day period, the Client shall be deemed to have accepted the use of the relevant Consultant's Drawing or Consultant's Specification for the construction of the Works to the extent that the document complies with the requirements of the Contract. 45.10 Documents become part of the Consultant's Design A Consultant's Drawing or Consultant's Specification submitted under clause 45.5 or resubmitted in accordance with clause 45.8(a) shall become part of the Consultant's Design: - when the Client has accepted that Consultant's Drawing or Consultant's Specification may be used for the construction of the Works pursuant to clause 45.7(d), or - where such acceptance is deemed to have occurred pursuant to clause 45.9. 45.11 Documentation program The Consultant shall, as part of any Program which it is obliged to provide pursuant to clause 12, submit a documentation program to the Client setting out the order in which and times by which Consultant's Drawings and Consultant's Specifications for the construction of the Works are to be completed and submitted to the Client. The Consultant shall ensure that the documentation program provides for, and makes due allowance for, those Consultant's Drawings and Consultant's Specifications to be prepared and supplied to the Client within the time required by and at a rate consistent with the maintenance of progress of the Works as advised by the Client. 45.12 Certification of the Works The Consultant shall, if required under Item 33 or requested by the Client, hand over the following to the Client: - three sets of “for construction” Consultant's Construction Drawings and Consultant's Construction Specifications in a form and containing such details as may be required by the Client, and - a Designer's Certificate certifying that the as-constructed Consultant's Construction Drawings and Consultant's Construction Specifications comply with the requirements of the Contract and the Consultant's Design. 45.13 Ambiguities and discrepancies in the Consultant's Design Clause 5.2 shall apply to Deliverables only where the ambiguity or discrepancy is in the Client Information. Where the ambiguity or discrepancy is: - in the Consultant's Design or any drawing or specification produced by the Consultant in respect of the Works (including in or between any of the Consultant's Construction Drawings or the Consultant's Construction Specifications), or - between the Consultant's Design or any drawing or specification produced by the Consultant in respect of the Services (including any Consultant's Construction Drawings or the Consultant's Construction Specifications) and the Client's Requirements, such ambiguity or discrepancy shall be at the Consultant's risk and the Direction under clause 5.3 shall not entitle the Consultant to any extra payment or an extension of time.

# WORKPLACE GENDER EQUALITY

Add a new clause 46 as follows:

46 WORKPLACE GENDER EQUALITY This clause applies if the Consultant is a relevant employer within the meaning of the WGE Act. The Consultant must comply with its obligations under the WGE Act and remain compliant until the expiry or termination of the Contract. The Consultant must take reasonable steps to ensure that any subcontractors comply with the WGE Act if that subcontractor is a relevant employer within the meaning of the WGE Act.

# MONTHLY REPORT

Add a new clause 47 as follows:

47 MONTHLY REPORT This clause only applies if stated at Item 34. On or before the end of each calendar month the Consultant shall give the Client a written report on the progress of the Services in the form and containing the detail required by the Client, which includes but is not limited to a summary of: - the activities carried out during that month; - the overall progress of the Services in accordance with the Program; and - any issues relating to the Fee, including any variations to the Services which may increase or have increased the Fee.

# 48	CONSULTANT AS LOCAL PROVIDER

Add a new clause 48 as follows:

48 CONSULTANT AS LOCAL PROVIDER ## 48.1 This clause 48 applies where the total Fee payable under this Contract exceeds $55,000.00 (including GST). 48.2 The Consultant must ensure that at all times during the term it is a Local Provider, unless a written exemption is provided by the Client. 48.3 The Consultant acknowledges that the Consultant’s failure to comply, in whole or in part, with the requirements of this clause 48 may result in suspension from the Department prequalification system for a period determined by the Client and shall constitute a substantial breach of the Contract by the Consultant for the purposes of clause 27.2, and may be a factor taken into account in the award of future contracts for the Government of South Australia, in addition to any other remedies available to the Client under this Contract. 48.4 The Consultant must provide to the Client, such information as the Client may require to verify the Consultant’s compliance with this clause. 48.5 The Consultant authorises the Client and its nominated agent to obtain information about the Consultant relevant to assessing the Consultant’s compliance with this clause, that may be held by any Government department or instrumentality. 48.6 In this clause “Local Provider” means a business that operates in South Australia, where greater than 50% of the workforce to deliver the Services are residents of South Australia.

# 49 SECURITY

Add a new clause 49 as follows:

49 SECURITY This clause 49 only applies if stated in Annexure Item 35. 49.1 The Consultant must ensure that all the Consultant’s Personnel involved in delivering the Services have the appropriate checks and security clearances before commencing any work on the Services. 49.2 Without limiting any of the requirements of clause 49.1, the Consultant must: (a) complete a National Police Check for all Consultant’s Personnel delivering the Services; and (b) obtain and provide to the Client such other checks and security clearances specified in Annexure Item 36 and as otherwise reasonably required by the Client. 49.3 The details of the checks and clearances under clause 49.2(b) must be agreed by the Client and conducted and provided to the Client prior to the commencement of each Consultant’s Personnel’s involvement in the Services and thereafter at such other times required by the Client and notified to the Consultant. 49.4 Following receipt of any check or security clearance required under this clause 49, the Client may conduct further investigations of Consultant’s Personnel, including criminal history, habits, associations, referee, character, security, and financial checks, in order to determine whether in the Client’s opinion the Consultant’s Personnel is suitable to be involved in providing the Services. If, after having conducted the further investigations, the Client is of the opinion that the Consultant’s Personnel is not suitable to be involved in the Services, the Client may notify the Consultant in writing of its determination, and on receipt of such notice the Consultant must cease to use the Consultant’s Personnel in the provision of the Services. In making a determination pursuant to this clause the Client is not obliged to act in good faith or give procedural fairness or give reasons for its decision. The Client will not be liable in respect of any claim against the Client in connection with a determination made by the Client pursuant to this clause, and the Consultant will indemnify and keep indemnified the Client against every such claim. 49.5 All clearances and checks required will be at the Consultant’s cost. 49.6 The Client may require the Consultant to not commence using any Consultant’s Personnel or to cease to use any Consultant’s Personnel in the provision of the Services who in the opinion of the Client: - do not comply with clauses 49.2 or 49.3; or - should not be used in the provision of the Services. 49.7 If the Client takes action under clause 49.6: - the Consultant must immediately take action to replace the relevant Consultant’s Personnel member; and - the Client will not be liable in respect of any associated claim and the Consultant will indemnify and keep indemnified the Client against every such claim.

# 50 AUDITOR GENERAL

Add a new clause 50 as follows:

50 AUDITOR GENERAL Nothing in this Contract derogates from the powers of the Auditor-General under the Public Finance and Audit Act 1987 (SA).

# 51 AUSTRALIAN GOVERNMENT AGREEMENT

Add a new clause 51 as follows:

51 AUSTRALIAN GOVERNMENT AGREEMENT This clause 51 shall only apply if stated to apply at Item 38. For the purpose of this clause 51 the following definitions shall apply: ‘Agreement’ means the agreement between the Commonwealth of Australia and State of South Australia that will be entered for the provision of funds for the Project; The Consultant acknowledges that the State will enter into an Agreement. The Consultant agrees to cooperate in all respects during the life of the Contract to enable the State to perform its obligations under the Agreement and without limitation, the Consultant will: - preserve the confidentiality of the Commonwealth Funding Agreement; - not do anything or permit anything to be done (whether by act or omission) which may cause or contribute towards a breach of the Agreement by the State or otherwise prejudice the Agreement; - provide any information requested by the Commonwealth pursuant to the Agreement. In the event that the Commonwealth either: - terminates the Agreement; or - otherwise withdraws funding for the Project, then the Client has the right to terminate this Contract with no liability to the Client, except that the Client will pay the Consultant for services rendered prior to such termination.

# 52 AUDIT

Add a new clause 52 as follows:

52 AUDIT 52.1 The Client may, at its own expense, at any time prior to Completion and for 12 months thereafter carry out or cause to be carried out an audit of any aspect of the operations of the Consultant relating to this Contract. The scope of the audit shall not include: - the Contractor’s profitability; - confidential personal information; and - Intellectual Property Rights such as designs, methods or innovations that do not have a direct link to the Contract deliverables. 52.2 Upon production of the written authorisation or appointment by the Client, the Consultant must, for the purpose of any such audit, permit the Client or any person engaged by the Client for that purpose: - to question and observe any Consultant’s Personnel engaged in relation to this Contract in the presence of a representative of the Consultant; and - to have full and sufficient access to any premises, storage facilities, records (excluding personnel records), Books and Records relevant to the performance by the Consultant of its obligations under this Contract. 52.3 The Client may for the purpose of auditing the Consultant’s performance under this Contract carry out such investigations as it considers necessary. The Client will provide reasonable notice and identification when conducting such investigations. 52.4 In the exercise of its rights under this clause the Client must minimise, so far as is practicable, any inconvenience or interruptions to the business of the Consultant or the performance by the Consultant of its obligations under this Contract. 52.5 If an audit carried out under this clause reveals a material breach of the Consultant’s obligations under this Contract or confirms a default previously denied by the Consultant, then the Consultant must pay all costs and expenses incurred by the Client in relation to the audit. 52.6 If an audit carried out under this clause does not identify a material breach of the Consultant’s obligations under this Contract or any non-conformance by the Consultant, the Consultant is entitled to reimbursement by the Client of its actual and reasonably incurred costs of the audit to be evidenced on an open book basis. 52.7 Following completion of any audit, the Consultant must meet with the Client to discuss in good faith any recommendations made. 52.8 The Consultant will at its own cost act upon and implement any reasonable recommendations made by the Client arising from the results of an audit under this clause.

# 53 OPERATION OF PROPORTIONATE LIABILITY LEGISLATION

Add a new clause 53 as follows:

53 OPERATION OF PROPORTIONATE LIABILITY LEGISLATION 53.1 To the extent permitted by law, the operation of Part 3 of the Law Reform (Contributory Negligence and Apportionment of Liability) (Proportionate Liability) Act 2001 (SA), and any equivalent statutory provision is excluded in relation to all rights, obligations and liabilities in connection with the Contract whether such rights, obligations or liabilities are sought to be enforced as a breach of contract or a claim in tort or otherwise. 53.2 The Consultant acknowledges that this clause 53 constitutes a special limitation for the purposes of Part 3 of the Law Reform (Contributory Negligence and Apportionment of Liability) (Proportionate Liability) Act 2001 (SA). 53.3 If the Consultant breaches any of its obligations under this Contract, and the operation of any legislation results in the Client being unable to recover some part of the consequential loss or damage from the Consultant (“the Apportioned Loss”), as a separate obligation under the Contract, the Consultant indemnifies the Client in respect of the Apportioned Loss and must pay the Client the amount of the Apportioned Loss if demanded by the Client.

ANNEXURE

This annexure takes the place of Part A of the Annexure to the General Conditions of Contract for Consultants (AS 41222010).

|  | Item |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 |  | Client (clause 1.1) |  | The Minister for Infrastructure and Transport ABN 92 366 288 135 The Commissioner of Highways ABN 45 751 448 902 The Rail Commissioner ABN 23 251 040 528 |  |  |
|  | 2 |  | Consultant (clause 1.1) |  | ACN ABN |  |  |
|  | 3 |  | The Contract Documents are: (Clause 1.1) |  | 1. These Special Conditions of Contract for Consultants to AS4122-2010, including their annexure and attachments |  |  |
|  |  |  |  |  | 2. The General Conditions of Contract for Consultants (as amended) AS4122-2010 |  |  |
|  |  |  |  |  | 3. The Scope |  |  |
|  | 4 |  | The Scope is described in the following Documents, set out at Attachment 4: |  | ………………………………………………………………………………. |  |  |
|  |  |  | (Clause 1.1) |  | ………………………………………………………………………………. |  |  |
|  | 5 |  | The purpose(s) for which the Services will be suitable is/are: (Clause 5.1) |  | ………………………………………………………………………………. |  |  |
|  |  |  |  |  | ………………………………………………………………………………. |  |  |
|  |  |  |  |  | ………………………………………………………………………………. |  |  |
|  | 6 |  | The Client's Representative (Clause 6.1) |  |  |  |  |
|  |  |  |  |  | Phone |  |  |
|  |  |  |  |  | Email |  |  |
|  | 7 |  | The Consultant's Representative (Clause 6.2) |  |  |  |  |
|  |  |  |  |  | Phone |  |  |
|  |  |  |  |  | Email |  |  |
|  | 8 |  | Basis for payment |  | Lump Sum OR Schedule of Rates OR Upper Limiting Fee, with the Fee not to exceed [insert] (including GST). |  |  |
|  |  |  | If Lump Sum is applicable, Lump Sum is: |  | $ insert (including GST) OR Not applicable |  |  |
|  |  |  | If Schedule of Rates is applicable, specify rates, or location of attached or agreed Schedule of Rates: |  | Refer to Schedule of Rates at Attachment 3 OR Not applicable |  |  |
|  |  |  | If Upper Limiting Fee is applicable, Upper Limiting Fee is: |  | $ insert (including GST) OR Not applicable |  |  |
|  |  |  | Claims for payment will be: |  | Paid as a single Lump Sum OR Paid upon completion of stages OR Paid monthly |  |  |
|  |  |  | If paid as a single Lump Sum, specify when it will be paid: |  |  |  |  |
|  |  |  | If paid upon completion of stages, specify stages and percentage of Fee to be paid on completion of each stage: |  | Stage/Task | Percentage of Fee |  |
|  |  |  |  |  | ……………………………………… | ……………………………………… |  |
|  |  |  |  |  | ……………………………………… | ……………………………………… |  |
|  |  |  |  |  | ……………………………………… | ……………………………………… |  |
|  | 9 |  | Disbursements for which the Consultant may claim payment: (Clause 10.2) |  | Refer to Schedule of Rates at Attachment 3 OR Not applicable |  |  |
|  | 10 |  | Time to claim payment is no later than: (Clause 10.3) |  | Last Business Day of each month |  |  |
|  | 11 |  | The time for payment is no later than: (Clause 10.6) |  | 15 days from receipt of a compliant invoice. |  |  |
|  | 12 |  | The rate of interest for overdue payment is: (Clause 10.9) |  | 8% per annum |  |  |
|  | 13 |  | The Date for Completion is: (Clause 12.1) |  | insert date OR insert time period from the Commencement Date |  |  |
|  | 14 |  | Other causes of delay for which the Consultant may notify an extension of time: (Clause 12.7) |  | None. |  |  |
|  | 15 |  | The Approvals to be obtained by the Consultant are: (Clause 13.2) |  |  |  |  |
|  | 16 |  | The key personnel are: (Clause 18) |  | Name | Role |  |
|  |  |  |  |  | ……………………………………… | ……………………………………… |  |
|  |  |  |  |  | ……………………………………… | ……………………………………… |  |
|  |  |  |  |  | ……………………………………… | ……………………………………… |  |
|  |  |  |  |  | ……………………………………… | ……………………………………… |  |
|  |  |  |  |  | ……………………………………… | ……………………………………… |  |
|  | 17 |  | Existing Conflicts of Interest (Clause 19.2) |  |  |  |  |
|  | 18 |  | The alternative that applies to Copyright and other Intellectual Property Rights is: (Clause 21.3) |  | Alternative Two |  |  |
|  | 19 |  | List of excluded Intellectual Property Rights: (Clause 21.3, Alternative Two) |  | None. |  |  |
|  | 20 |  | The additional amount payable to the Consultant for granting of Intellectual Property Rights to the Client is: (Clause 21.4, Alternative Two) |  | Not applicable |  |  |
|  | 21 |  | Does Clause 22 (Moral Rights) apply? (Clause 22.1) |  | No |  |  |
|  | 22 |  | Not Used. |  |  |  |  |
|  | 23 |  | Not Used |  |  |  |  |
|  | 24 |  | The Consultant's liability is limited to: (Clause 29.1) |  | The greater of 100% of the Fee or the amount of the relevant insurance in Item 25 or Item 26 as the case may be. |  |  |
|  | 25 |  | The amount of public liability insurance is: (Clause 30.2) |  | $10,000,000 if the Fee is $10,000,000 or less. $20,000,000 if the Fee is greater than $10,000,000. and in any case, the above amount is per occurrence and in aggregate. |  |  |
|  | 26 |  | The amount of professional indemnity insurance is: (Clause 30.4) |  | $1,000,000 if the Fee is $1,000,000 or less. $5,000,000 if the Fee is greater than $1,000,000 but equal to or less than 5,000,000. $10,000,000 if the Fee is greater than $5,000,000 but equal to or less than 10,000,000. $20,000,000 if the Fee is greater than $10,000,000. and in any case, the above amount is per occurrence and in aggregate. |  |  |
|  | 27 |  | The professional indemnity insurance must be maintained for the following period: (Clause 30.4) |  | 7 years from completion of the Services. |  |  |
|  | 28 |  | The Client must effect the following insurances and maintain them for the following periods: (Clause 30.7) |  | Not applicable |  |  |
|  | 29 |  | The address of service of Notices on the Client is: (clause 33.1) |  | Director, Department for Infrastructure and Transport Level X, 83 Pirie St, Adelaide SA 5000 |  |  |
|  |  |  | The address for service of Notices on the Consultant is: (Clause 33.3) |  |  |  |  |
|  | 30 |  | The law governing this Contract is: (Clause 35) |  | South Australia |  |  |
|  | 31 |  | Consultants Design: Does clause 45 apply? (Clause 45) |  | Yes OR No |  |  |
|  | 32 |  | Consultant’s Industry Participation Plan: Does clause 41 apply? (Clause 41) |  | Yes OR No |  |  |
|  | 33 |  | Are the documents referred to in clause 45.12 required? (Clause 45.12) |  | Yes OR No |  |  |
|  | 34 |  | Are monthly reports required? (Clause 47) |  | Yes OR No |  |  |
|  | 35 |  | Are checks and security clearances required? (Clause 49) |  | Yes OR No |
|  | 36 |  | Checks and security clearances required include: (Clause 49) |  | National Police Check [Insert other checks and clearances required (eg negative vetting) and specify level (if appropriate)] |  |
|  | 37 |  | Is a Statutory Declaration Required? (Clause 10.4A(d)) |  | Yes OR No |
| 38 |  | Australian Government Agreement – does Clause 51 apply? (Clause 51) |  | Yes OR No |  |  |  |

ATTACHMENT 1 - INDUSTRY PARTICIPATION POLICY OR NOT USED

ATTACHMENT 2 - DESIGNER'S CERTIFICATE OR NOT USED

DESIGNER'S CERTIFICATE

To:

Name and address of Client

| From: |  |
| --- | --- |
| Name and address of Consultant |  |
| Please tick applicable boxes below (Clause references are to the General Conditions of Contract in the Contract between the Client and the Consultant) |  |
| ☐ | Submission of Drawings I certify that the Drawings and Specifications detailed from Page 2 of this Designer's Certificate: - comply in all respects with the requirements of clause 45 of the General Conditions of Contract - were prepared in accordance with the quality assurance system implemented by the Consultant relating to design. |
| ☐ | Completion of Works- clause 45.12 of General Conditions of Contract I certify that - the design of the Works complies with the Contract - the drawings and specifications comply with the Contract |

Terms used in this certificate bear the meanings given to them in the Contract between the Client and the Consultant.

| Authorisation |  |  |
| --- | --- | --- |
| (Must be a principal of the Consultant) |  |  |
| Name/Position | Signature | Date |

| Drawing/Specification reference | Description |
| --- | --- |

ATTACHMENT 3 – SCHEDULE OF RATES OR NOT USED

ATTACHMENT 4 - SCOPE

ATTACHMENT 5 – DEED OF NOVATION

DEED OF NOVATION

between

[INSERT CONSULTANT]

(ACN [INSERT])

(“Continuing Party”)

and

[INSERT OTHER SA GOVERNMENT ENTITY]

(ACN [INSERT])

(“New Party”)

and

MINISTER FOR INFRASTRUCTURE AND TRANSPORT

Or

COMMISSIONER OF HIGHWAYS

Or

RAIL COMMISSIONER

(“Retiring Party”)

DEED OF NOVATION made on this ………......…..day of ……......................………. 20...

BETWEEN:

[INSERT CONSULTANT] 			(“Continuing Party”)

AND

[INSERT]

(“New Party”)

AND

COMMISSIONER OF HIGHWAYS

Or

RAIL COMMISSIONER

Or

MINISTER FOR INFRASTRUCTURE AND TRANSPORT		(“Retiring Party”)

BACKGROUND

A.	The Retiring Party and the Continuing Party entered into contracts specified in the Schedule for the provision of [insert description of services] (“Contracts”).

B.	The Continuing Party and the Retiring Party agree to novate the Contracts.

C.	The Continuing Party agrees to release and discharge the Retiring Party from the operation of the Contracts.

D.	The New Party undertakes to perform the obligations of the Retiring Party under the Contracts in accordance with the terms and conditions of this Deed.

THE PARTIES AGREE AS FOLLOWS:

# NOVATION

The parties agree that the Contracts are novated on the basis that the Contracts continue in existence except that as at the date of this Deed:

## the Retiring Party ceases to be a party to the Contracts;

## the New Party becomes a party to the Contracts; and

## the Continuing Party continues to be a party to the Contracts.

# RELEASE OF RETIRING PARTY

The Retiring Party is released and discharged from the date of this Deed from:

## its obligations under the Contracts; and

## any claims accruing under the Contracts before the date of this Deed;

## any claims accruing under the Contracts from the date of this Deed for which it would have been liable had it continued to be a party to the Contracts.

# OBLIGATIONS OF THE NEW PARTY

## From the date of this Deed, the New Party is bound by the terms of the Contracts and must perform the obligations of the Retiring Party as if it were named in the Contracts as a party to those Contracts in place of the Retiring Party.

## From the date of this Deed, the New Party assumes liability for claims which accrued beforeon or after the date of this Deed for which the Retiring Party would have been liable had it continued to be a party to the Contracts.

# INDEMNITY BY RETIRING PARTY

  - The Retiring Party must keep the New Party indemnified from all claims against the New Party arising from liabilities which accrued before the date of this Deed for which the Retiring Party is, or would have been, liable had it continued to be a party to the Contracts.

  - For clarity, only the New Party is entitled to make a claim against the Continuing Party in connection with the Contracts.

# COSTS OF THIS DEED

Each party must pay its own costs arising from the preparation and execution of this Deed.  The New Party must pay the stamp duty assessed on this Deed.

EXECUTED AS A DEED

THE COMMON SEAL of [INSERT]	)

)

(ACN [INSERT])	)

)

was affixed hereto	)

)

in the presence of:	)

)

……………………………………………

[INSERT]

Witness

Print Name:

THE COMMON SEAL of [INSERT]	)

)

(ACN [INSERT])	)

)

was hereunto affixed	)

)

in the presence of:	)

Director

Print Name:

Director/Secretary

Print Name:

THE COMMON SEAL of [INSERT]	)

)

(ACN [INSERT])	)

)

was hereunto affixed	)

)

in the presence of:	)

Director

Print Name:

Director/Secretary

Print Name:

# SCHEDULE

Contracts entered into between Continuing Party and the Retiring Party:

# Contract No XCXXX,

# Contract Name,

Dated

# Contract No XCXXX,

# Contract Name,

Dated

ATTACHMENT 6 – TENDER FORM

ATTACHMENT 7 - STATUTORY DECLARATION

STATUTORY DECLARATION

Oaths Act 1936(SA)

DEFINITIONS

The Client is:	»

The Consultant is:	»

The Contract:	The contract between the Client and the 	Consultant

Contract Title:	»

Contract Number:	»

Dated:	»……………	(Date of Contract) between the party 	identified as the Client and the party identified 	as the Consultant.

Declaration

Full  Name:	I »………………………………………………

of»

»

do hereby truly and solemnly declare the following and I make this solemn declaration conscientiously believing the same to be true, and by virtue of the provisions of the Oaths Act 1936 (SA):

      - I am the director or project manager of the Consultant and authorised by the Consultant to make this statutory declaration on its behalf.

      - I am in a position to make this statutory declaration about the facts attested to.

      - On each day during the period from the Commencement Date until the date of this statutory declaration:

        - the Consultant has operated as a business in South Australia; and

        - greater than 50% of the Consultant’s workforce involved in delivering the Services were residents of South Australia.

I acknowledge that this declaration is true and correct and I make it with the understanding and believe that a person who makes a false declaration may be guilty of an offence.

Signature of Declarant:

declared at:

Place: 	»

on»

before me:

Signature of legally authorised

person* before whom the

declaration is made:				……………………………………………………….

Name and title of person*

before whom the declaration

is made					……………………………………………………….

This declaration was signed/ initialled by electronic means. [Statement to be included if the declaration was signed electronically]

This declaration was taken remotely under the observation of the authorised witness through an audio-visual link and the requirements under the Oaths Act 1936 for taking declarations by audio visual link were complied with. [Statement to be included if the declaration was witnessed remotely online]

I certify that the following modifications were made to the witnessing process:

[Details to be included of any assistance the witness provided to the declarant. For example, state here that the statement was read to the declarant and/or they nodded their agreement]

Signature of legally authorised person* before whom the declaration is made:

……………………………………………………….

[Name and address of any other person who assisted the declarant to make the declaration (not including assistance in a professional capacity to prepare/ write the declaration on the instructions of the declarant)]

[Nature of assistance the other person provided, eg translation assistance]

* The declaration must be made before one of the following persons:

- a Commissioner for taking affidavits in the Supreme Court

- a person who is registered as a conveyancer under the Conveyancers Act 1994

- a justice of the peace

- a police officer, other than a police officer who is a probationary constable

- persons admitted and enrolled as a notary public of the Supreme Court;

- an agent of the Australian Postal Corporation in charge of an office supplying postal services to the public

- an Australian Consular Officer or an Australian Diplomatic Officer within the meaning of the Consular Fees Act 1955 of the Commonwealth

- a bailiff

- a bank officer who has 5 or more years of continuous service

- a building society officer who has 5 or more years of continuous service

- a chief executive officer of a Commonwealth court

- a clerk of a court

- a credit union officer who has 5 or more years of continuous service

- an employee of the Australian Trade and Investment Commission who is in a country or place outside Australia; and is authorised under paragraph 3(d) of the Consular Fees Act 1955 of the Commonwealth; and is exercising their function in that place

- an employee of the Commonwealth who is (i) in a country or place outside Australia; and (ii) authorised under paragraph 3(c) of the Consular Fees Act 1955 of the Commonwealth; and (iii) exercising their function in that place

- a fellow of the National Tax and Accountants' Association

- a registered health practitioner

- a finance company officer who has 5 or more years of continuous service

- a marriage celebrant registered under Part IV Division 1 Subdivision C of the Marriage Act 1961 of the Commonwealth

- a member of the Governance Institute of Australia

- a member of Engineers Australia, other than at the student grade

- a member of the Association of Taxation and Management Accountants

- a member of the Australasian Institute of Mining and Metallurgy

- a member of the Australian Defence Force who is— (i) an officer; or (ii) a non-commissioned officer within the meaning of the Defence Force Discipline Act 1982 of the Commonwealth who has 5 or more years of continuous service; or (iii) a warrant officer within the meaning of the Defence Force Discipline Act 1982 of the Commonwealth

- a member of the Institute of Chartered Accountants in Australia, CPA Australia (Certified Public Accountants) or the Institute of Public Accountants;

- a Member of— (i) the Parliament of the Commonwealth; or (ii) the Parliament of a State; or (iii) a Territory legislature; or (iv) a local government authority of a State or Territory

- a minister of religion registered under Part IV Division 1 Subdivision A of the Marriage Act 1961 of the Commonwealth

- a patent attorney or a trade marks attorneys

- a permanent employee of the Australian Postal Corporation who has 5 or more years of continuous service who is employed in an office supplying postal services to the public

- a permanent employee of

- the Commonwealth or a Commonwealth authority

- a State or Territory or a State or Territory authority

- a local government authority, with 5 or more years of continuous service who is not specified in another item in this list

- a Senior Executive Service employee of— (i) the Commonwealth or a Commonwealth authority; or (ii) a State or Territory or a State or Territory authority

- a sheriff

- a sheriff's officer

- a teacher employed on a full-time basis at a school or tertiary education institution

- a veterinary surgeon.

ATTACHMENT 8 -